## Operations Input
2010-01-31 | Start Time For Operations
2009-09-22 06:00 |  | 0 |  |  | 0
Macondo, MC 252 | OCSG-24102, MC 727 # 2 | [7 empty] | MMS
[9 empty] | 14 | 30 | 30 | Concurrent Operations |  | Concurrent Operations
Start Time | Operation Description | Workshop Target Time | Daily Working Estimate | Actual Operation Skipped (Y or N) | Actual Time | Variance (AAR) | Hole Section Total Target Time | Hole Section Actual Total Time | BOP | CSG | Caliper | Main Rotary | General comments and/or reasons for NPT | Mouse hole | Moon pool | Deck / Other
2010-01-31 | Activities at GC743#5 | 0 | 0 |  | 0 |  | 0 | 0
2010-01-31 | Prepare for move | 0 | 0 |  | 0 |  | 0 | 0
2010-01-31 | Transit to MC 252 f/ MC 727 | 0 | 11 |  | 0 |  | 0 | 0
2010-01-31 11:00 |  | 0 | 0 |  | 0 |  | 0 | 0
2010-01-31 11:00 |  | 0 |  |  | 0 |  | 0 | 0
2010-01-31 11:00 |  | 0 |  |  | 0 |  | 0 | 0
2010-01-31 11:00 | Arrive MC 252, perform Sea Trials | 0 | 6 |  | 0 |  | 0 | 0 |  |  |  | MOB | SURE | MOB
2010-01-31 17:00 |  | 0 |  |  | 0 |  | 0 | 0
2010-01-31 17:00
2010-01-31 17:00
2010-01-31 17:00
2010-01-31 17:00 | Perform BOP Maintenance | 0 | 147 |  | 145 | [6 empty] | MOB | SURE | MOB
2010-02-06 18:00 | DIMS PHASE: LNR1 18-1/8" X 22"Hole Section, 18" Liner
2010-02-06 18:00 | Hold pre job safety meeting on R/U riser handling equipment |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-06 18:30 | R/U Riser Running Equipment |  | 3 |  | 3 | 0 | [5 empty] | DOF | LNR1 | BOPSUB
2010-02-06 21:30 | P/U crossover Jt & 1 Jt , move BOP's to well center |  | 1.5 |  | 1.5 | 0 | [5 empty] | DOF | LNR1 | BOPSUB
2010-02-06 23:00 | M/U Crossover to Stack and RIH fm surface to 177' MD |  | 1 |  | 1 | 0 | [5 empty] | DOF | LNR1 | BOPSUB
2010-02-07 | R/U chicksan lines & fill lines with water |  | 1 |  | 0.5 | 0 | [5 empty] | DOF | LNR1 | BOPSUB
2010-02-07 00:30 | Test rigid conduit & boost lines |  | 1.5 |  | 1.5 | 0 | [5 empty] | DOF | LNR1 | BOPSUB
2010-02-07 02:00 | Run riser | 0 | 24 |  | 24.5 | [6 empty] | DOF | LNR1 | BOPSUB |  | 1.5 hours due to NPT experienced with Riser Skate & Gantry Crane Downtime.
2010-02-08 02:30 | PU & lowered slip joint into position. |  | 2 |  | 2.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 05:00 | Held pre-job safety meeting on nipple up hoses | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 05:30 | Working over water. Installed & test hoses in moonpool. Latch up SDL ring. |  | 2 |  | 1.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 07:00 | Test Lines | 0 | 1 |  | 1
2010-02-08 08:00 | Move rig, land out, latched up stack & locked WH connector. |  | 2 |  | 4 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 12:00 | RU &Installed air lines to packer on slip joint. L/D landing joint & riser running tool. PU & install diverter. |  | 4 |  | 5.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 17:30 | RD riser handling equipment. LD diverter running tool. |  | 4 |  | 4 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-08 21:30 | P/U part of 18 1/8" BHA, P/U Dril-Quip Test Tool | 0 | 1 |  | 4 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 01:30 | Function Diverter | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 02:00 | RIH w/ BOP test plug, P/U Test Kelly, Land out test plug | 0 | 2.5 |  | 3.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 05:30 | Test Connector & Blind shear rams | 0 | 1 |  | 1.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 07:00 | POOH, L/D Dril-Quip Test Tool | 0 | 2.5 |  | 3 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 10:00 | Finish P/U 18 1/8" Clean out BHA | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 11:00 | RIH w/ 18 1/8" BHA, Space out 6 5/8" across stack | 0 | 2.5 |  | 4 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 15:00 | P/U & test lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-09 15:30 | Pressure Test BOP components per APD |  | 7 |  | 11 |  |  |  | x |  |  | DOF | LNR1 | BOPSUB
2010-02-10 02:30 | Fuction Test BOPs | 0 | 0.5 |  | 0 |  |  |  | x |  |  | DOF | LNR1 | BOPSUB
2010-02-10 03:00 | R/D Chicksan Lines & L/D Test Kelly | 0 | 1 |  | 1 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 04:00 | POOH to 5126' | 0 | 1 |  | 1 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 05:00 | RIH to To 5814' | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 05:30 | Change Out IBOP & Test | 0 | 10 |  | 7 | [6 empty] | DOF | LNR1 | BOPSUB |  | NPT-Rig Repair Transocean
2010-02-10 12:30 | Held pre-job safety meeting on testing csg | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 13:00 | Performed Csg integrity test (Not MMS) | 0 | 1 |  | 1 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 14:00 | R/D Chicksan Lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 14:30 | TIH to TOC @ 5814'. |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 15:00 | Drill cement plug and displace with SBM while drilling. |  | 4 |  | 4 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-10 19:00 | Wash down to 18" Liner Top 7,479' | 0 | 5.5 |  | 5.5
2010-02-11 00:30 | CBU | 0 | 1.5 |  | 1.5
2010-02-11 02:00 | Flow Check - 30 Minutes | 0 | 0.5 |  | 0.5
2010-02-11 02:30 | POOH and laydown clean-out BHA |  | 2.5 |  | 5 | [6 empty] | DOF | LNR1 | BOPSUB
2010-02-11 07:30 | Perform Casing Test per APD | 0 | 2 |  | 1 |  |  |  |  | X
2010-02-11 08:30 | Pick up 16-1/2" x 20" BHA |  | 6 |  | 1 | [6 empty] | DOF | LNR1 | CEMT
2010-02-11 09:30 | Program MWD Tools | 0 | 1 |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-02-11 10:30 | Continue P/U 16 1/2" x 20" BHA | 0 | 3 |  | 3.5 | [6 empty] | DOF | LNR3 | CEMT |  | Picked up HWDP of Skate -Extra Time
2010-02-11 14:00 | TIH W/ BHA to 1524' | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR4 | CEMT |  | Stopped to repair pumps on trip tank
2010-02-11 14:30 | Repair Trip Tank Pump | 0 | 1 |  | 1 | [6 empty] | DOF | LNR5 | CEMT |  | NPT - Transocean Rig Repair
2010-02-11 15:30 | TIH to 4000' -Shallow test MWD Tools | 0 | 1 |  | 1 | [6 empty] | DOF | LNR6 | CEMT
2010-02-11 16:30 | TIH to Shoe Track | 0 | 4 |  | 2 | [6 empty] | DOF | LNR7 | CEMT
2010-02-11 18:30 | Drill cement & shoe track and 10' new hole to 9086'. |  | 5 |  | 12.5 | [6 empty] | DOF | LNR1 | CEMT
2010-02-12 07:00 | Circulate B/U to Wellhead |  | 1 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT
2010-02-12 07:30 | Flow Check, POH to 8,956' for LOT | 0 | 0.5 |  | 0.5
2010-02-12 08:00 | Several Attempts to Conduct LOT. - Failed |  | 2.5 |  | 6 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality | Made 4 attempts w/ no success -
2010-02-12 14:00 | Pump Slug | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality | NPT-downhole failure-formation
2010-02-12 14:30 | R/D Chicksans - L/D Test Kelly | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-12 15:00 | Pump Out Of Hole to 7073' Looking for washout in pipe | 0 | 3.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-12 18:30 | Test Upper Annular | 0 | 1.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-12 20:00 | POH wet to BHA | 0 | 5.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality | Pulled BHA only to repin DQ Wear Sleeve
2010-02-13 01:30 | Repin DQ Wear Sleev & RIH to 4000' | 0 | 3 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 04:30 | Shallow test MWD Tools | 0 | 0.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 05:00 | TIH to 8956' | 0 | 2 |  | 3 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 08:00 | Wash to 9086' | 0 | 0.5 |  | 0
2010-02-13 08:30 | CBU to wellhead | 0 | 1 |  | 2 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 10:30 | POH to 8953' , P/U test kelly & R/U Lines | 0 | 0.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 11:00 | Attempt LOT at 18" Shoe | 0 | 1.5 |  | 1 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality | Failed LOT - Will Squeeze
2010-02-13 12:00 | POH Wet | 0 | 2 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 14:00 | Pump Slug & POOH to BHA |  | 4 |  | 3 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 17:00 | L/D BHA |  | 1.5 |  | 3.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 20:30 | Squeeze 18" Shoe | 0 |  |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 20:30 | Pre Job Safety Meeting | 0 | 0.5 |  | 0
2010-02-13 21:00 | R/U 3 1/2" Handling Tools | 0 | 0.5 |  | 0
2010-02-13 21:30 | P/U 1214' of Cmt 3 1/2" Stinger in Doubles |  | 2 |  | 1.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-13 23:00 | R/D 3 1/2" Handling tools | 0 | 0.5 |  | 0
2010-02-13 23:30 | TIH to 9086' |  | 2 |  | 2.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 02:00 | CBU to wellhead | 0 | 2.5 |  | 0
2010-02-14 04:30 | P/U Cmt kelly & R/U Lines | 0 | 0.5 |  | 0
2010-02-14 05:00 | Mix / Pump Cement per procedure |  | 1 |  | 2 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 07:00 | POH w/ 9 stands to 7853', Close Annular |  | 0.5 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 08:00 | Drop nerf ball & circ 1 DP volume | 0 | 0.5 |  | 0
2010-02-14 08:30 | Squeeze / Displace cmt |  | 0.5 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 09:30 | Hold press & WOC 6 hrs (Final 243 psi) |  | 6 |  | 5.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 15:00 | Bleed off press (1.25 bbls) | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 15:30 | Pump slug, R/D Chicksan lines & L/D Cmt kelly | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 16:00 | POH W/ Cmt Stinger |  | 2 |  | 1.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 17:30 | Safety meeting / R/U 3 1/2" tools | 0 | 1 |  | 1 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 18:30 | L/D 3 1/2" Stinger |  | 2 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 19:30 | R/D 3 1/2" Tools & clear floor | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 20:00 |  | 0 |  |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 20:00 | Clear floor & Service rig | 0 | 1 |  | 1 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 21:00 | Pre Job Safety meeting | 0 | 0.5 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 21:30 | Start Pick up 16-1/2" x 20" BHA |  | 1 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 22:30 | Program MWD Tools | 0 | 0.5 |  | 0.5 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-14 23:00 | Continue P/U 16 1/2" x 20" BHA | 0 | 2 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 | TIH W/ BHA to 3998' | 0 | 1 |  | 1 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 01:00 | Shallow test MWD Tools | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 01:30 | TIH to 8679' | 0 | 2 |  | 2.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 04:00 | Wash down to TOC (8866') | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 04:30 | Drill Cement |  | 1.5 |  | 4 | 0 | [5 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 08:30 | Drill 10' new formation | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 09:00 | C & C Mud | 0 | 2.5 |  | 2.5 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 11:30 | POH to 8953' , P/U test kelly & R/U Lines | 0 | 1 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality
2010-02-15 12:30 | LOT at 18" Shoe | 0 | 1 |  | 0 | [6 empty] | DOF | LNR1 | CEMT | NPT - Cmt - Poor Quality | Good LOT - Drill Ahead
2010-02-15 13:30
2010-02-15 13:30 | Drill 16-1/2"
2010-02-15 13:30 | Drill f/ 9096' to 11,887' (74 ft/hr average). |  | 37.5 |  | 37.5 | [6 empty] | DOF | LNR2 | DRILL
2010-02-17 03:00 | Sperry Rebooted ADI System | 0 | 1 |  | 1 | [6 empty] | DOF | LNR2 | DRILL |  | NPT-Sperry Drilling
2010-02-17 04:00 | Drill f/ 11,887' to 12,12,246' | 0 | 4.5 |  | 4.5 | [6 empty] | DOF | LNR2 | DRILL
2010-02-17 08:30 | Circulate out gas & Raise M/W 11.1 to 11.4 ppg | 0 | 9 |  | 12.5 | [6 empty] | DOF | LNR2 | DRILL |  | Time Estimated Only
2010-02-17 21:00 | Drill f/ 12,246' to 12,350' MD | 0 | 2 |  | 2 | [6 empty] | DOF | LNR2 | DRILL |  | ECD'S came up to 11.72 ppg
2010-02-17 23:00 | Circ to clean out hole and lower ECD's | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | DRILL
2010-02-17 23:30 | Started Losing Returns | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns | Started losing full returns and flow decreased. Total mud lost - 121 bbls.
2010-02-18 00:30 | Pump 174 bbl LCM Pill | 0 | 2 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns | Started losing 6 bbl/min, spotted LCM Pill and dropped to 4 bbl/min down to 1.6 bbl/min.
2010-02-18 02:30 | Monitor Well | 0 | 2 |  | 4.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns | After 30 min = 6.3 bbls lost, after 1 hr = 6.9 bbls total lost, after 2 hrs = 8.8 bbls total lost.
2010-02-18 07:00 | POOH to 8,908' MD | 0 | 4 |  | 4 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-18 11:00 | Break circ @ stage up mud pumps | 0 | 1 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-18 13:00 | Monitor Well - Lost Returns | 0 | 127.5 |  | 127.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-23 20:30 | CBU + 8,770' MD, Flow check, Took SCR's | 0 | 8 |  | 8 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 04:30 | Monitor Well | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 05:00 | POOH to BHA | 0 | 7 |  | 7 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 12:00 | L/D BHA | 0 | 2 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 14:00 | Slip & Cut Drill Line + service rig | 0 | 1.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 17:00 | P/U Clean out BHA + Pre-job Safety Meeting | 0 | 2 |  | 1.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 18:30 | RIH to +/-4,000 | 0 | 2.5 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 20:30 | Shallow test MWD Tools | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 21:00 | RIH to 6,726' MD | 0 | 2 |  | 1.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 22:30 | P/U & test lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-24 23:00 | Pressure Test BOP components per APD |  | 1 |  | 1 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 | Pressure Test BOP components per APD | 0 | 7 |  | 6 |  |  |  | x
2010-02-25 06:00 | Fuction Test BOPs | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 06:30 | R/D Chicksan Lines & L/D Test Kelly | 0 | 0.5 |  | 0.5
2010-02-25 07:00 | RIH from 6,726' MD to 8,770' MD | 0 | 1.5 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 09:00 | Stage up pumps to 400 gpm | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 10:30 | Wash & Ream to 9,300' MD (Circulate as needed to lower ECD) | 0 | 3.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 13:30 | Circulate Bottoms up | 0 | 4.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 16:30 | Wash & Ream to 9,878' MD (Circulate as needed to lowere ECD) | 0 | 3.5 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 18:30 | Circulate Bottoms up to Wellhead | 0 | 4.5 |  | 1 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 19:30 | Ream to 10,433' MD (Circulate as needed to lower ECD) | 0 | 3.5 |  | 2 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-25 21:30 | Circulate Bottoms up | 0 | 4.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-26 00:30 | Ream to 10,984' MD (Circulate as needed to lower ECD) | 0 | 3.5 |  | 2.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-26 03:00 | Circulate bottoms up | 0 | 4.5 |  | 6.5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-26 09:30 | Ream to 11,395' MD (Circulate as needed to lower ECD) | 0 | 3.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-26 12:30 | Circulate bottoms up | 0 | 4.5 |  | 9 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-26 21:30 | Ream to 11,638' MD (Circulate as needed to lower ECD) | 0 | 3.5 |  | 3 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-27 00:30 | Circulate bottoms up | 0 | 5 |  | 5 | [6 empty] | DOF | LNR2 | LCR | NPT - Downhole Problems - Lost Returns
2010-02-27 05:30 | Spot 600 bbls of 13.5 PPG mud |  | 1 |  | 1 | [6 empty] | DOF | LNR2 | DRILL
2010-02-27 06:30 | POOH to 10,580' MD |  | 1 |  | 1 | [6 empty] | DOF | LNR2 | DRILL
2010-02-27 07:30 | Repair Racker | 0 | 0.5 |  | 0.5
2010-02-27 08:00 | POOH to 8,800' MD (Inside 18" Shoe) | 0 | 1 |  | 2
2010-02-27 10:00 | Circulate bottoms up | 0 | 4.5 |  | 2.5
2010-02-27 12:30 | Flow Check | 0 | 0.5 |  | 0.5
2010-02-27 13:00 | POOH wet OH. Pump slug. POOH OH to ML. Retrieve wear sleeve. |  | 7 |  | 5 | [6 empty] | DOF | LNR2 | DRILL
2010-02-27 18:00 | RB & LD part of BHA. |  | 2 |  | 2.5 | [6 empty] | DOF | LNR2 | DRILL
2010-02-27 20:30 | Cement, Case, Test |  |  |  | 1
2010-02-27 21:30 | RU Weatherford 16" csg slips & elevators. |  | 2 |  | 2.5 | [6 empty] | DOF | LNR2 | CASE |  | Offloading BHA items & 16" casing equipment.
2010-02-28 | Held pre-job safety meeting | 0 | 0.5 |  | 0.5
2010-02-28 00:30 | PU & run 16" 4,367' MD |  | 16 |  | 11.5 | [6 empty] | DOF | LNR2 | CASE |  | 8 Joints per hour
2010-02-28 12:00 | Held pre-job safety meeting | 0 |  |  | 0.5
2010-02-28 12:30 | Repaired weld on bracket on 16" handling tools | 0 |  |  | 0.5
2010-02-28 13:00 | P/U & run 16" to 6,335' MD | 0 |  |  | 3.5
2010-02-28 16:30 | R/D Csg Elevator OES, R/U DP Elevator | 0 |  |  | 1
2010-02-28 17:30 | P/U & M/U casing hanger. Release & LD csg running tool. |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CASE
2010-02-28 18:00 | R/D Casing Equipment, R/U 750 ton bails |  | 1 |  | 2 | [6 empty] | DOF | LNR2 | CASE
2010-02-28 20:00 | RIH w/ 16" casing. Run landing string. TIH w/ 16" csg f/ to Depth. |  | 5 |  | 6 | [6 empty] | DOF | LNR2 | CASE
2010-03-01 02:00 | PU cmt head. Land out 16" csg hanger. Shift ATC diverter |  | 1 |  | 1 | [6 empty] | DOF | LNR2 | CASE
2010-03-01 03:00 | Held pre-job safety meeting | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 03:30 | R/U & Cmt 16". R/D Cmt Equipment. |  | 3.5 |  | 4.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 08:00 | Set seal assy.Tested lines.Tested seal assy . |  | 1 |  | 2 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 10:00 | LD cement head. Pull 25 std landing string, circ 2 wiper balls |  | 1 |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 11:00 | Pump slug. |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 11:30 | POOH f/ ML to Surf. L/D DrilQuip equipment. |  | 3.5 |  | 3 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 14:30 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 15:00 | Held pre-job safety meeting (BHA) | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 15:30 | Start Picking 14 3/4" Bit & MWD Assy | 0 | 1 |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 16:30 | Program MWD Tools | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 17:00 | Continue M/U 14¾" x 16 1/2" BHA. |  | 2 |  | 2 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 19:00 | TIH to ML. Test Casing |  | 2 |  | 3 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 22:00 | Shallow Test MWD Tools | 0 | 0.5 |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-01 23:30 | TIH from ML to TOC. Pump up ESD. |  | 4 |  | 5.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 05:00 | Raise mud weigh & Circulate above bha | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 05:30 | Wash 100', Drill cmt & shoe track to 11,587' MD |  | 6.5 |  | 7.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 13:00 | Losing mud, monitored well | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 13:30 | Cut Mud Weight back | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 14:30 | Monitored well | 0 |  |  | 2.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 17:00 | POOH to 11,450 | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 17:30 | Monitored well | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 19:00 | Pump 160 bbls of 11.5 ppg LCM Pill | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 20:30 | Monitor well | 0 |  |  | 2 | [6 empty] | DOF | LNR2 | CEMT
2010-03-02 22:30 | Closed upper annular, boost riser & cut mud weight | 0 |  |  | 4 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 02:30 | Open annular & monitor well | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 03:30 | Cut Mud Weight back | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 04:30 | Cut mud weight in the riser | 0 |  |  | 5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 09:30 | Open annular & monitor well | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 10:00 | Broke circulation & wash down | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 10:30 | Monitored well at 11,575' md | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 12:00 | Held pre-job safety meeting on POOH | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 12:30 | POOH from 11,575' md to 8,127' md | 0 |  |  | 3 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 15:30 | Broke circulation & Circulate 11.3 ppg mud around | 0 |  |  | 4 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 19:30 | RIH to 9,826' md at 4 minutes per stand | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-03 21:00 | Broke circulation & Circulate 11.3 ppg mud around | 0 |  |  | 3 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 | Held pre-job safety meeting on RIH | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 00:30 | RIH to 10,513' md | 0 |  |  | 0.5
2010-03-04 01:00 | Trouble shot PRS | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 01:30 | RIH to 11,519', Washed down to 11,615' md | 0 |  |  | 5.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 07:00 | Monitor Well on the trip tank, losing mud | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 08:00 | Spot 180 bbls of 84 lb/bbl LCM Pill | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 09:00 | Monitor well, losing 30 bph | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 09:30 | POOH to 11,475' md | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 10:00 | Trouble shot PRS | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 11:00 | POOH to 10,605' md | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 12:00 | Monitor well, losing 12 bph | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 13:30 | Pumped 40 bbls 13.7 ppg slug | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 14:00 | POOH to 8,859' MD at 5 minutes per stand | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 15:30 | Function Test Bops | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 16:00 | POOH to 1,292' MD | 0 |  |  | 5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 21:00 | Rack back HWDP | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 22:00 | Held pre-job safety meeting - L/D BHA | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-04 22:30 | L/D BHA | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 | Clear & Clean Floor | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 00:30 | Service Top Drive | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 01:00 | R/U 3 1/2" Handling Tools | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 01:30 | RIH w/ 3 1/2" Tubing | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 03:00 | R/D 3 1/2" Handling tools | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 03:30 | RIH w/ 3 1/2" Tubing on 6 5/8" DP | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 04:00 | Trouble shot forward finger board | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 04:30 | Continue RIH w/ 3 1/2" on 6 5/8" DP | 0 |  |  | 4 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 08:30 | Picked up Cement kelly | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 09:00 | Pumped down CST Tool | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 10:00 | R/U Chicksan lines, monitored well, losing mud at 12 bph | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 10:30 | Perform Cement Job | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 12:00 | Displaced Cement | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 12:30 | R/D Chicksan Lines & L/D Test Kelly | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 13:00 | POOH 9 stands | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 13:30 | Drop nerf ball & circ 1 string volume | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 14:00 | R/U chicksan lines & tested to 3,000 psi | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 14:30 | Closed lower annular & halliburton squeezed cement | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 15:30 | Hold pressure & monitor | 0 |  |  | 2.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 18:00 | Opened annular & monitored well | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 18:30 | R/D Chicksan Lines & L/D Test Kelly | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 19:00 | Pumped slug | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 19:30 | POOH to 3 1/2" Tubing | 0 |  |  | 3.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 23:00 | Held pre-job safety meeting | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-05 23:30 | R/U 3 1/2" Handling Tools | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 | Held pre-job safety meeting on L/D 3 1/2" | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 00:30 | POOH L/D 3 1/2" Tubing | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 01:30 | R/D 3 1/2" Handling tools | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 02:00 | Held pre-job meeting - On picking up BHA | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 02:30 | Picked up 14 3/4" x 16 1/2" BHA | 0 |  |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 03:00 | Program MWD Tools | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 04:00 | Continue p/u 14 3/4" x 16 1/2" BHA | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 05:30 | RIH w/ 14 3/4" x 16 1/2" BHA | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 06:30 | Fill Pipe & Shallow Test Lines | 0 |  |  | 1 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 07:30 | Slip & Cut drill line + service rig | 0 |  |  | 1.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 09:00 | RIH w. 14 3/4" x 16 1/2" BHA to 10,605' MD | 0 | 3.5 |  | 2.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 11:30 | Wash & Ream to TOP of Cement 11,145 | 0 | 0.5 |  | 2 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 13:30 | Drill Cement to 11,600' MD | 0 | 7.5 |  | 9 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 22:30 | Circ Cutting above BHA | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 23:00 | Perform Initial FIT | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-06 23:30 | Circulate & weight up to 11.5 ppg | 0 | 5 |  | 3 | [6 empty] | DOF | LNR2 | CEMT
2010-03-07 02:30 | Drill cmt & Wash 20' of Rat Hole | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-07 03:00 | Circ Cutting above BHA | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-07 03:30 | POH to 16" Shoe | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR2 | CEMT
2010-03-07 04:00 | P/U Test kelly & R/U Lines, Perform LOT test . | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 04:30 | Washed down to 11,634' MD | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 05:30 | DIMS PHASE: LNR3 14-3/4" x 16-1/2" Hole Section, 13-5/8" Liner | 0 |  |  | 0
2010-03-07 05:30 | Circulate Bottoms Up | 0 | 2.5 |  | 2 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 07:30 | Wash & ream to 11,895' md (reamer not open) | 0 | 2.5 |  | 2.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 10:00 | Circulate Bottoms Up | 0 | 2 |  | 2 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 12:00 | Wash & Ream to 12,107' md (reamer not open) | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 13:30 | Circulate Bottoms Up | 0 | 2.5 |  | 2.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 16:00 | Pump Hi vis sweep & Jaring on pipe | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 17:00 | Staged up pumps & weighted up to 11.7 ppg | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 18:00 | Wash & Ream to bottom of rathole | 0 | 3 |  | 3 | [6 empty] | DOF | LNR3 | DRILL
2010-03-07 21:00 | Pump Sweep & Circulate bottoms up | 0 | 3 |  | 3 | [6 empty] | DOF | LNR3 | DRILL
2010-03-08 | Pumped out of the hole to 11,731' MD | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | DRILL
2010-03-08 01:00 | Activated Reamer & Verified Open | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-08 01:30 | Wash & Ream with Reamer open to bottom | 0 | 6 |  | 6.5 | [6 empty] | DOF | LNR3 | DRILL
2010-03-08 08:00 | Drill 14-3/4" x 16-1/2" Hole | [10 empty] | DOF | LNR3 | DRILL
2010-03-08 08:00 | Drill ahead from 12,360 to 12,852 ' (Raise mud weight per weight up schedule) |  | 7 |  | 7 | [6 empty] | DOF | LNR3 | DRILL |  | Figured at 70' per hour
2010-03-08 15:00 | Circulate bottoms up to lower ECD | 0 | 2 |  | 1.5 | [6 empty] | DOF | LNR3 | DRILL |  | ECD reached 12.41- Circulate to lower ECD
2010-03-08 16:30 | Drill ahead from 12,852 to 13,305 ' (Raise mud weight per weight up schedule) | 0 | 5 |  | 5.5 | [6 empty] | DOF | LNR3 | DRILL |  | Figured at 60' per hour
2010-03-08 22:00 | Trouble Time - Kick / Stuck Pipe | 0 |  |  | 0 | [6 empty] | DOF | LNR3 | DRILL
2010-03-08 22:00 | Took kick, stuck pipe, packed off, no circulation | 0 | 0 |  | 2 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-09 | Monitor SICP & SIDPP | 0 |  |  | 16.5 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-09 16:30 | Bled SIDPP F/ 310 psi to 0 psi, Monitor for 10 min, Install safety valve | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-09 17:00 | Boost riser & monitor SICP & SIDPP | 0 |  |  | 30 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-10 23:00 | Bled SIDPP F/ 150 psi to 0 psi, Monitor for 10 min, Install safety valve | 0 |  |  | 1 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-11 | Wireline Operations / Fishing | 0 |  |  | 0 | [6 empty] | DOF | LNR4 | DRILL
2010-03-11 | Safety Meeting on R/U Schlumberger Wireline | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-11 00:30 | Remove Lubricator cap, P/U Gauge Ring Tools |  | 0 |  | 1 | 0 | [5 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-11 01:30 | Howco test Lubricator | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-11 02:00 | Schlumberger 2.8" Gauge Ring Run | 0 |  |  | 5 | [6 empty] | DOF | LNR3 | DRILL |  | NPT Time: Well Control & Stuck Pipe
2010-03-11 07:00 | RIH W/ Schlumberger Bond Log Run (Tool left in pipe) | 0 | 14.5 |  | 14.5 | [6 empty] | DOF | LNR3 | DRILL |  | 6 hours NPT - Stuck bond log inside of 6 5/8" DP
2010-03-11 21:30 | R/D Schlumberger | 0 | 2.5 |  | 2.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 | R/U Smith Wireline | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 01:30 | Test Lubricator | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 02:00 | Smith Gauge Run | 0 | 4.5 |  | 3 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 05:00 | Smith Run to set 3.71" Magna Range Plug | 0 | 7 |  | 3.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 08:30 | Smith run to sever the HWDP | 0 | 14 |  | 3.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 12:00 | R/D Smith Wireline | 0 | 3 |  | 3 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-12 15:00 | Kill Well | 0 |  |  | 47 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 14:00 | Open well & Monitor / Well static | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 14:30 | CBU @ 12,100' | 0 | 5 |  | 4.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 19:00 | Observe well on trip tank for 30 min. | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 19:30 | CBU again | 0 |  |  | 3.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 23:00 | Flow check / L/D 2 singles | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 |  | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-14 23:30 | Mix / Pump Cement Plug #1per procedure | 0 |  |  | 2 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 01:30 | L/D cmt kelly / POH to 11,850' | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 02:00 | Drop nerf ball & CBU | 0 |  |  | 6 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 08:00 | TIH & Tag CMT to test Firmness / poh to 11,831' | 0 |  |  | 3 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 11:00 | Circ & WOC | 0 |  |  | 1.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 12:30 | Tag cmt for firmness 15k @11,683' | 0 |  |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 13:00 | POH to 11,529' | 0 |  |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 14:00 | P/U test kelly & R/U Lines | 0 |  |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 15:00 | Test BOPS while WOC | 0 | 7.5 |  | 8 |  |  |  | X |  |  | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 23:00 | Function Test Bops | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-15 23:30 | POH & L/D severed HWDP | 0 | 5 |  | 5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 04:30 | P/U 3 1/2" Cmt Stinger | 0 | 2 |  | 2 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 06:30 | TIH to 11,850' | 0 | 5 |  | 4 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 10:30 | CBU | 0 | 3.5 |  | 3.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 14:00 | P/U Cmt kelly & R/U Lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 14:30 |  | 0 |  |  | 0 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 14:30 | Pump Cement Plug #2 (Kick off ) | 0 | 2 |  | 2 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 16:30 | Pull out of cmt to 11,150' MD | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 17:30 | Drop nerf ball & circ 1 DP volume | 0 | 0.5 |  | 4 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-16 21:30 | POH to 3 1/2" tbg |  | 5 |  | 4 | 0 | [5 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 01:30 | L/D 3 1/2" cmt stinger | 0 | 2 |  | 2 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 03:30 |  | 0 |  |  | 0 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 03:30 | Held pre-job meeting - on slip/cut drill lne | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 04:00 | slip and cut drill line | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 05:00 | Hold pre job meeting on p/u BHA | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 05:30 | Picked up 14 3/4" x 16 1/2" BHA | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 06:30 | Program MWD Tools | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 07:30 | Continue p/u 14 3/4" x 16 1/2" BHA | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 09:00 | RIH w/ 14 3/4" x 16 1/2" BHA 4,000' +/- | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 10:00 | Fill Pipe & Shallow Test MWD tools | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 10:30 | RIH w. 14 3/4" x 16 1/2" BHA to TOC | 0 | 3.5 |  | 3.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 14:00 | Wash & Ream fm 11,303' MD to 11,554' MD | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 15:00 | CBU and cut mud wt to 12.1 ppg | 0 | 5.5 |  | 5.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 20:30 | Wash & Ream fm 11,554' MD to 11,600' MD | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-17 21:00 | Dress off and drill cement fm 11,600' MD - 11,675' MD | 0 | 3 |  | 3.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-18 00:30 | Drill 14-3/4" x 16-1/2" Hole fm 11,700' MD 11,838' MD | 0 | 3.5 |  | 3.5 | [6 empty] | DOF | LNR3 | Remcmt | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-18 04:00 | Backream fm 11,838' MD to 11,695' MD | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-18 04:30 | Drop ball, activate reamer | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control | NPT Time: Well Control & Stuck Pipe
2010-03-18 05:30 | Drill 14-3/4" x 16-1/2" hole section to 13,100' +/- | 0 | 30 |  | 24 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control | Estimated @ 60 fph
2010-03-19 05:30 |  |  | 0 | [8 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 05:30 | Circulate Bottoms up | 0 | 5 |  | 6 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 11:30 | Flow check | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 12:00 | POOH to 16" Shoe | 0 | 4 |  | 3 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 15:00 | POOH f/ csg shoe to ML |  |  |  |  | 0 | [5 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 15:00 | Flow check |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 15:30 | POOH from ML to surface |  | 2 |  | 5 | 0 | [5 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 20:30 | L/D & R/B BHA. |  | 2.5 |  | 2 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 22:30 | Cleaning and clearing the rig floor. |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | STKOH | NPT: Well Control
2010-03-19 23:00 | Cement, Case, Test | [10 empty] | DOF | LNR3 | CASE
2010-03-19 23:00 | Rigging up 13-5/8" casing running tools |  | 2.5 |  | 2 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 01:00 | P/U 13-5/8" Shoe Track & Csg | 0 | 5.5 |  | 5.5
2010-03-20 06:30 | Pump 40 bbls mud |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 07:00 | RD casing equipment & R/U to RIH w/ casing on dp. |  | 1.5 |  | 1 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 08:00 | P/U W'ford Liner Hgr | 0 | 0.5 |  | 0.5
2010-03-20 08:30 | Clean & Clear Rig Floor | 0 | 1 |  | 1
2010-03-20 09:30 | TIH w/ 13-5/8" casing f/ surf to land out |  | 9 |  | 9.5 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 19:00 | P/U & M/U cement head .Shift ATC diverter sub |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 19:30 | Set hanger & release. |  | 2 |  | 3.5 | [6 empty] | DOF | LNR3 | CASE
2010-03-20 23:00 | Cmt 13-5/8" liner. |  | 3 |  | 2.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 01:30 | PU string to (neutral). Prepare to test liner top packer. |  | 0.5 |  | 1 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 02:30 | Verify packer is set . R/D cement line & L/D cement head. |  | 1 |  | 0.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 03:00 | Drop wiper ball, circ 2 string volume. Flow Check |  | 1 |  | 1 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 04:00 | POOH w/ 13-5/8" running tool to surface. |  | 6 |  | 5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 09:00 | 6 Hour Post Casing Rig Maintenance | 0 | 6 |  | 6
2010-03-21 15:00 | P/U 12-1/4" x 14-1/2" BHA |  | 1 |  | 1 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 16:00 | Program MWD Tools |  | 0.5 |  | 1.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 17:30 | Continue P/U 12-1/4" x 14-1/2" BHA | 0 | 1 |  | 2.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 20:00 | RIH w/ BHA to M/L Test casing and BSR while TIH. |  | 2 |  | 1 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 21:00 | Shallow Test MWD Tools | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR3 | CEMT
2010-03-21 22:00 | RIH to 12,709' MD | 0 | 1 |  | 4.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-22 02:30 | Function Test Bops | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-22 03:00 | RIH fm 12,709' MD to 12,954' MD | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR3 | CEMT |  | Tagged float collar @ 12,954' MD
2010-03-22 03:30 | Drill shoe track. Wash through rathole to TD . Drill 10' of new formation. C&C. |  | 7 |  | 7 | [6 empty] | DOF | LNR3 | CEMT |  | Drilled Float Collar fm 12,954' MD to 13,
2010-03-22 10:30 | Pull into shoe |  | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-22 11:00 | Circulate prior to FIT | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | CEMT |  | Pump up static density of 12.72 ppg with 12.5 # mud.
2010-03-22 12:00 | R/U Test Lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR3 | CEMT
2010-03-22 12:30 | Perform FIT | 0 | 1 |  | 1 | [6 empty] | DOF | LNR3 | CEMT |  | Max pressure = 1,480 psi. equilevent mud wt = 14.6 ppg. Pumped up static density of 14.71 ppg max.
2010-03-22 13:30 | TIH to TD. Circ and raise mud wt |  | 0.5 |  | 3 | [6 empty] | DOF | LNR3 | CEMT |  | Circ at 13,160' MD & raise mud wt from 12.5 ppg to 12.8 ppg.
2010-03-22 16:30 | DIMS PHASE: 12-1/4" x 14 1/2" Hole Section | [10 empty] | DOF | LNR4 | DRILL
2010-03-22 16:30 | DRILL 12-1/4" x 14 1/2" HOLE | [10 empty] | DOF | LNR4 | DRILL
2010-03-22 16:30 | Drill to 15,000' . Pump 40 bbl 13.6 ppg sweep every other stand. |  | 35 |  | 36.5 | [6 empty] | DOF | LNR4 | DRILL |  | Est on 70' per hour. At 13,276' MD, drop Baker reamer ball. No perssure spike observed.
2010-03-24 05:00 | CBU. Flow Check. |  | 4 |  | 6.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-24 11:30 | POOH to 13 5/8" Casing Shoe | 0 |  |  | 2.5
2010-03-24 14:00 | POOH f/ TD to Casing Shoe |  | 2 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-24 14:30 | Flow check at Shoe |  | 1 |  | 1 | [6 empty] | DOF | LNR4 | DRILL
2010-03-24 15:30 | POOH f/ shoe to ML |  | 2 |  | 2 | [6 empty] | DOF | LNR4 | DRILL
2010-03-24 17:30 | POOH f/ ML to BHA |  | 6 |  | 5.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-24 23:00 | L/D BHA | 0 | 1.5 |  | 1 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 | 11 7/8" Case, Cement, Test | 0 |  |  | 0 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 | Cleaned & Cleared Rig Floor | 0 | 0.5 |  | 0.5
2010-03-25 00:30 | Top drive service & drops survey | 0 | 0.5 |  | 0.5
2010-03-25 01:00 | Held Pre-Job safety meeting on R/U | 0 | 0.5 |  | 0.5
2010-03-25 01:30 | R/U Weatherford Casing Equipment | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 03:00 | Held Pre-Job safety meeting on running casing | 0 | 0.5 |  | 0.5
2010-03-25 03:30 | Pick up 11 7/8" Shoe Track | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 04:00 | Run 11 7/8" Casing | 0 | 4.5 |  | 3.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 07:30 | R/D Csg Elevator OES, R/U DP Elevator | 0 | 0.5 |  | 1 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 08:30 | P/U Versa-Flex Liner Hanger | 0 | 1 |  | 1 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 09:30 | RIH w/ 11 7/8" on 6 5/8" Landing String | 0 | 11 |  | 3.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 13:00 | P/U & M/U cement head .Shift ATC diverter sub |  | 0.5 |  | 7.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 20:30 | Rig up to perform cement job. | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 21:00 | Perform Cement job | 0 | 1 |  | 2 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 23:00 | Displace Cement | 0 | 3 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-25 23:30 | Expand Liner Top | 0 | 2.5 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 | Pressure test 11 7/8" Liner top | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 00:30 | POOH wet | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 01:00 | Drop Nerf ball & Circulate 1.5 DP Vol | 0 | 1 |  | 1 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 02:00 | Pump 50 bbl Slug | 0 | 1 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 02:30 | POOH & L/D running tool | 0 | 6 |  | 4.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 07:00 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | LNR4 | DRILL
2010-03-26 07:30 | Held PreJob Safety Meeting | 0 | 0.5 |  | 0.5
2010-03-26 08:00 | P/U 10 5/8" x 12 1/4" BHA | 0 | 1 |  | 1.5
2010-03-26 09:30 | Program MWD Tools | 0 | 0.5 |  | 1.5
2010-03-26 11:00 | Finish P/U 10 5/8" x 12 1/4" BHA | 0 | 1.5 |  | 1
2010-03-26 12:00 | Held Prejob Safety Meeting | 0 | 0.5 |  | 0.5
2010-03-26 12:30 | Shallow Test MWD Tools/ Cont. Running In Hole | 0 | 1.5 |  | 2
2010-03-26 14:30 | Slip Drill line & Casing Test | 0 | 2 |  | 2 |  |  |  |  | x
2010-03-26 16:30 | RIH To 9,259' MD | 0 | 2 |  | 2
2010-03-26 18:30 | Pick Up 5 1/2" Test Pipe. Cont RIH | 0 | 3.5 |  | 3.5
2010-03-26 22:00 | Space out 5 1/2" Test pipe across stack | 0 | 1 |  | 1
2010-03-26 23:00 | R/U Chiksan Lines | 0 | 1 |  | 1
2010-03-27 | Test Bop On 5 1/2" Test Pipe | 0 | 3.5 |  | 3.5
2010-03-27 03:30 | R/D Chiksan Lines & Test Kelly | 0 | 0.5 |  | 0.5
2010-03-27 04:00 | RIH To 14,503' MD | 0 | 0.5 |  | 0.5
2010-03-27 04:30 | Test BOP On 6 5/8" | 0 | 3.5 |  | 3.5 |  |  |  | X
2010-03-27 08:00 | Function Test BOP's | 0 | 0.5 |  | 0.5
2010-03-27 08:30 | RIH to TOC | 0 | 0.5 |  | 0.5
2010-03-27 09:00 | Wash 100', Drill cmt, float collar, cement |  | 7 |  | 7
2010-03-27 16:00 | Circulated above top of 11 7/8" | 0 | 0.5 |  | 0.5
2010-03-27 16:30 | Take SCR's & Perform D5 Drill | 0 | 1 |  | 1
2010-03-27 17:30 | Flush C&K | 0 | 0.5 |  | 0.5
2010-03-27 18:00 | Drilled cement & Shoe + 10' new formation | 0 | 2.5 |  | 2.5
2010-03-27 20:30 | Circulated above top of 11 7/8" | 0 | 0.5 |  | 0.5
2010-03-27 21:00 | R/B Stand & P/U Test Kelly | 0 | 0.5 |  | 0.5
2010-03-27 21:30 | Perform LOT | 0 | 1 |  | 1
2010-03-27 22:30 | R/D Lines | 0 | 0.5 |  | 0.5
2010-03-27 23:00 |  | 0 |  |  | 0
2010-03-27 23:00 | Drill 10 5/8" x 12 1/4" | 0 |  |  | 0 | [6 empty] | DOF | PROD1 | DRILL
2010-03-27 23:00 | Circulate & weight up to 13.6 ppg | 0 | 3 |  | 3
2010-03-28 02:00 | RIH to Bottom | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | PROD1 | DRILL
2010-03-28 02:30 | Drill 10 5/8" x 12 1/4" Hole to +/- 17,200' MD | 0 | 40 |  | 40 | [6 empty] | DOF | PROD1 | DRILL |  | Figured at 50' per hour
2010-03-29 18:30 | Circulate bottoms up | 0 | 5.5 |  | 6.5 | [6 empty] | DOF | PROD1 | DRILL
2010-03-30 01:00 | POOH wet to the shoe | 0 | 1 |  | 2 | [6 empty] | DOF | PROD1 | DRILL
2010-03-30 03:00 | Flow check | 0 | 0.5 |  | 0.5 | [6 empty] | DOF | PROD1 | DRILL
2010-03-30 03:30 | Pump slug | 0 | 0.5 |  | 0.5
2010-03-30 04:00 | POOH to BHA | 0 | 8 |  | 8 | [6 empty] | DOF | PROD1 | DRILL
2010-03-30 12:00 | Safety Meeting L/D BHA | 0 | 0.5 |  | 0.5
2010-03-30 12:30 | L/D BHA | 0 | 1.5 |  | 1.5 | [6 empty] | DOF | PROD1 | DRILL
2010-03-30 14:00 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0.5
2010-03-30 14:30 | R/U Weatherford 9 7/8" Casing Equipment | 0 | 1 |  | 1
2010-03-30 15:30 | Safety Meeting Running 9 7/8" Casing | 0 | 0.5 |  | 0.5
2010-03-30 16:00 | Pick up 9- 7/8" Shoe Track | 0 | 1 |  | 1
2010-03-30 17:00 | Run 9- 7/8" Casing | 0 | 3 |  | 3
2010-03-30 20:00 | R/D Csg Elevator OES, R/U DP Elevator | 0 | 1 |  | 1
2010-03-30 21:00 | P/U Versa-Flex Liner Hanger | 0 | 0.5 |  | 0.5
2010-03-30 21:30 | RIH w/ 9-7/8" on 6 5/8" Landing String | 0 | 11 |  | 9
2010-03-31 06:30 | M/U cement head, circulate & wash down |  | 1.5 |  | 1.5
2010-03-31 08:00 | Rig up to perform cement job. | 0 | 0.5 |  | 0.5
2010-03-31 08:30 | Perform Cement job | 0 | 1 |  | 1
2010-03-31 09:30 | Displace Cement | 0 | 3 |  | 1.5
2010-03-31 11:00 | Expand Liner Top, Pressure test 9-7/8" Liner top | 0 | 2.5 |  | 1
2010-03-31 12:00 | Safety meeting | 0 | 0.5 |  | 0.5
2010-03-31 12:30 | Drop Nerf ball & Circulate 1.5 DP Vol | 0 | 1 |  | 1.5
2010-03-31 14:00 | Pump 75 bbl Slug | 0 | 1 |  | 0.5
2010-03-31 14:30 | POOH & L/D running tool | 0 | 6 |  | 6
2010-03-31 20:30 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0.5
2010-03-31 21:00 | Perform 6 hour post casing maintenance | 0 | 6 |  | 6
2010-04-01 03:00 | Unpinned RBS | 0 | 0 |  | 0.5
2010-04-01 03:30 | Held Prejob Safety Meeting | 0 | 0.5 |  | 0.5
2010-04-01 04:00 | P/U 8-1/2" BHA | 0 | 0.5 |  | 0.5
2010-04-01 04:30 | Program MWD Tools | 0 | 0.5 |  | 1
2010-04-01 05:30 | Finish P/U 8-1/2" BHA | 0 | 1 |  | 1
2010-04-01 06:30 | Change out die blocks | 0 |  |  | 0.5
2010-04-01 07:00 | P/U 5 1/2" HWDP (New pipe p/u) | 0 |  |  | 3.5
2010-04-01 10:30 | RIH to +/-4,000 | 0 | 1 |  | 1.5
2010-04-01 12:00 | Shallow Test MWD Tools | 0 | 0.5 |  | 0.5
2010-04-01 12:30 | Test Casing to 914 psi & function test blind shears | 0 |  |  | 2 |  |  |  |  | x
2010-04-01 14:30 | RIH to 14,195' MD | 0 | 4.5 |  | 4.5
2010-04-01 19:00 | Shallow Test MWD Tools | 0 |  |  | 0.5
2010-04-01 19:30 | RIH to 16,946' MD | 0 | 2 |  | 0.5
2010-04-01 20:00 | Circulate & Condition | 0 |  |  | 2
2010-04-01 22:00 | Wash last stand down (Begin weighting up to 14.3 ppg) | 0 | 0.5 |  | 0.5 | [6 empty] | DOF
2010-04-01 22:30 | Wash 100', Drill cmt & Float Collar |  | 5 |  | 5 | [6 empty] | DOF
2010-04-02 03:30 | Perform D-5 Well Kill Drill | 0 | 1 |  | 1
2010-04-02 04:30 | Drill remainder of shoe track + 10' new formation | 0 | 1 |  | 1
2010-04-02 05:30 | Circulated above BOP's | 0 | 3 |  | 3
2010-04-02 08:30 | POOH & P/U Test Kelly & R/U Lines | 0 | 0.5 |  | 0.5
2010-04-02 09:00 | Perform FIT | 0 | 1 |  | 2 | [6 empty] | DOF
2010-04-02 11:00 | R/D Lines | 0 | 0.5 |  | 0.5 | [6 empty] | DOF
2010-04-02 11:30 | Washed to Bottom | 0 | 0.5 |  | 0.5
2010-04-02 12:00 | Drill to 17,321' MD | 0 | 4 |  | 4.5 | [7 empty] | 33' per hour
2010-04-02 16:30 | Drop ball, activate reamer | 0 | 0.5 |  | 1.5
2010-04-02 18:00 | Drill 8 1/2" x 9 7/8" hole to 17,761' MD | 0 |  |  | 7.5
2010-04-03 01:30 | Flow checked well, flowing | 0 |  |  | 0.5
2010-04-03 02:00 | Shut in & monitor | 0 |  |  | 6.5
2010-04-03 08:30 | Pumped 184 bbls of 84 lb/bbl LCM | 0 |  |  | 1
2010-04-03 09:30 | Drill 8-1/2" x 9 7/8" Hole to 17,835' MD | 0 |  |  | 1.5
2010-04-03 11:00 | Wash, Backream & re-log hole f/ 17,835' t/ 17,745' MD | 0 |  |  | 1
2010-04-03 12:00 | Washed down to 17,835' & take Geo-Tap Pressure | 0 |  |  | 1.5
2010-04-03 13:30 | CBU & cut mud weight to 14.3 ppg | 0 |  |  | 3
2010-04-03 16:30 | Pumped out of hole to 17,634' MD | 0 |  |  | 0.5
2010-04-03 17:00 | CBU & cut mud weight to 14.3 ppg | 0 |  |  | 3
2010-04-03 20:00 | Flow check at 17,634' MD, well static | 0 |  |  | 1
2010-04-03 21:00 | Function Test BOP's | 0 |  |  | 0.5
2010-04-03 21:30 | Took SCR's & Pumped LCM Pill | 0 |  |  | 1
2010-04-03 22:30 | Drill 8-1/2" Hole to +/- 18,260' MD | 0 | 45 |  | 22 | [7 empty] | Bit / Reamer trip (Not TD)
2010-04-04 20:30 | Control Lost Circulation Ops | 0 | 0 |  | 64.5
2010-04-07 13:00 | Flow Check | 0 | 0.5 |  | 0
2010-04-07 13:30 | Displace Choke / Kill Line W/ 14.0 Mud | 0 | 0.5 |  | 0
2010-04-07 14:00 | Take SCR'S | 0 | 0.5 |  | 0
2010-04-07 14:30 | POH Wet to 13,643' | 0 | 1.5 |  | 0
2010-04-07 16:00 | Pump Slug | 0 | 0.5 |  | 0
2010-04-07 16:30 | POH to BHA | 0 | 10 |  | 7.5
2010-04-08 | L/D BHA | 0 | 3.5 |  | 3
2010-04-08 03:00 | Clear & Clean Floor | 0 | 0.5 |  | 0.5
2010-04-08 03:30 | P/U New Bit & MWD Tool | 0 | 0.5 |  | 0.5
2010-04-08 04:00 | Program MWD Tools | 0 | 1.5 |  | 1
2010-04-08 05:00 | Finish P/U BHA & RIH W/ HWDP | 0 | 1 |  | 1.5
2010-04-08 06:30 | TIH to 4,874' | 0 | 1 |  | 1.5
2010-04-08 08:00 | Shallow Test MWD | 0 | 1 |  | 0.5
2010-04-08 08:30 | Perform Brake Test / Cut & Slip Drill Line | 0 | 2.5 |  | 2.5
2010-04-08 11:00 | Perform Drops survey | 0 | 0.5 |  | 0.5
2010-04-08 11:30 | TIH to top of 9 7/8" Liner 11,843' | 0 | 4 |  | 4
2010-04-08 15:30 | Investigate Dropped Oblest Incident | 0 | 1.5 |  | 1.5 | [7 empty] | NPT - Rig Reair - Aft PRS
2010-04-08 17:00 | Cont. TIH to top of 9 7/8" Liner 14,667' | 0 | 0.5 |  | 0.5
2010-04-08 17:30 | Break Circ & Stage pumps up to 300 gpm & circ | 0 | 0.5 |  | 1
2010-04-08 18:30 | TIH to 9 7/8" Shoe 17,144' | 0 | 2 |  | 1.5
2010-04-08 20:00 | Break Circ & Stage pumps up to 300 gpm & circ | 0 | 0.5 |  | 1
2010-04-08 21:00 | TIH to 17,668' | 0 | 0.5 |  | 0.5
2010-04-08 21:30 | Break Circ & Stage pumps up to 300 gpm & circ | 0 | 0.5 |  | 1.5
2010-04-08 23:00 | Wash to 17,686' | 0 | 1.5 |  | 3.5 | [7 empty] | Lost Returns
2010-04-09 02:30 | Monitor well for Lost Returns | 0 | 1 |  | 1
2010-04-09 03:30 | Pump LCM Pill & Regain Returns | 0 | 3 |  | 3
2010-04-09 06:30 | Wash to 18,260' | 0 | 0.5 |  | 0.5
2010-04-09 07:00 | Drill 8-1/2" Hole to TD (+/- 150') | 0 | 6 |  | 5.5 | [7 empty] | Estimated @ 45' fph depending on TD
2010-04-09 12:30 | C & C Mud & Clean Hole | 0 | 8 |  | 6.5
2010-04-09 19:00 | Pump out of hole to 17,001' | 0 | 2.5 |  | 2.5
2010-04-09 21:30 | Flow Check | 0 | 0.5 |  | 0.5
2010-04-09 22:00 | Position 6 5/8" test pipe across BOP - P/U test kelly & R/U lines | 0 | 1 |  | 1
2010-04-09 23:00 | Test Subsea Bop's on 6 5/8" DP | 0 | 4.5 |  | 4.5
2010-04-10 03:30 | R/D Lines & L/D Test Kelly | 0 | 0.5 |  | 0.5
2010-04-10 04:00 | POH to 16,667' | 0 | 1 |  | 1
2010-04-10 05:00 | M/U TDS, Circ hole due to drag | 0 | 0.5 |  | 0.5
2010-04-10 05:30 | P/U test kelly & R/U lines | 0 | 0.5 |  | 0.5
2010-04-10 06:00 | Test Subsea Bop's on 5 1/2"" DP | 0 | 2.5 |  | 2.5 |  |  |  | x
2010-04-10 08:30 | Function test BOP'S | 0 | 0.5 |  | 0
2010-04-10 09:00 | R/D Lines & L/D Test Kelly | 0 | 0.5 |  | 0.5
2010-04-10 09:30 | POH Wet to 14,759' TOL | 0 | 3 |  | 4
2010-04-10 13:30 | Pump Slug | 0 | 0.5 |  | 0.5
2010-04-10 14:00 | POH to BHA | 0 | 6.5 |  | 4.5
2010-04-10 18:30 | L/D BHA | 0 | 2 |  | 1.5
2010-04-10 20:00 | Clear & Clean Floor | 0 | 0.5 |  | 0 | [6 empty] | DOF
2010-04-10 20:30 |  | 0 |  |  | 0
2010-04-10 20:30 |  | 0 |  |  | 0
2010-04-10 20:30 | EVALUATE PRODUCTION HOLE-LOGGING
2010-04-10 20:30 | Safety meeting on R/U Wireline | 0 | 0.5 |  | 0
2010-04-10 21:00 | R/U Schlumberger Wireline | 0 | 1.5 |  | 2
2010-04-10 23:00 | Load radioactive source & test tools | 0 | 1 |  | 1
2010-04-11 | Descent #1: ZAIT-GPIT-LDS-CNT-GR-LEHQT | 0 | 8 |  | 6
2010-04-11 06:00 | Descent #2 CMR-ECS-HNGS-LEHQT | 0 | 10 |  | 0
2010-04-11 16:00 | Descent #3: Dual OBMI-GPIT-DSI-GR-Swivel-LEHQT | 0 | 10 |  | 11
2010-04-12 03:00 | Descent #4: MDT-GR-LEHQT | 0 | 24 |  | 29
2010-04-13 08:00 | Descent #5:MSCT-GR-LEHQT | 0 | 12 |  | 5.5
2010-04-13 13:30 | POOH w' MSCT Tools | 0 | 4.5 |  | 4.5 | [7 empty] | NPT- MSCT Tool Failure
2010-04-13 18:00 | RIH w' new MSCT Tool string | 0 | 2 |  | 2 | [7 empty] | NPT- MSCT Tool Failure
2010-04-13 20:00 | Descent #5:MSCT-GR-LEHQT / re-run | 0 | 2 |  | 0
2010-04-13 22:00 | POOH w' MSCT Tools | 0 | 4 |  | 4 | [7 empty] | NPT - MSCT Tool Failure
2010-04-14 02:00 | RIH w' USIC Tool string | 0 | 3 |  | 3 | [7 empty] | NPT - MSCT Tool Failure. Decision to run VSP walk away while waiting on more MSCT tools
2010-04-14 05:00 | Descent # 6: USIC | 0 | 12 |  | 10
2010-04-14 15:00 | Descent #5 Re-Run MSCT-GR-LEHQT | 0 | 18 |  | 16.5
2010-04-15 07:30 | R/D Wireline | 0 | 1.5 |  | 0.5
2010-04-15 08:00 | DIMS PHASE: ABAN (Suspend) | 0 |  |  | 0
2010-04-15 08:00 | Clean Out Trip | 0 |  |  | 0
2010-04-15 08:00 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0.5
2010-04-15 08:30 | P/U Clean out BHA | 0 | 1.5 |  | 2.5
2010-04-15 11:00 | RIH to 4,000' | 0 | 2 |  | 2.5
2010-04-15 13:30 | Fill Pipe & Shallow Test MWD tools | 0 | 0.5 |  | 0.5
2010-04-15 14:00 | RIH to Top of 9 7/8" Liner | 0 | 6.5 |  | 4
2010-04-15 18:00 | Stage up pumps & circ | 0 | 1 |  | 3
2010-04-15 21:00 | TIH to to 9 7/8" shoe | 0 | 1.5 |  | 2
2010-04-15 23:00 | Stage up pumps & circ | 0 | 1 |  | 1.5
2010-04-16 00:30 | TIH to 18, 100' +/- | 0 | 1 |  | 1.5
2010-04-16 02:00 | Wash to TD | 0 | 1 |  | 2
2010-04-16 04:00 | Pump sweep / C&C Mud | 0 | 8 |  | 0
2010-04-16 12:00 | POH to BHA / Pull Wear Sleeve | 0 | 15 |  | 0
2010-04-17 03:00 | L/D BHA | 0 | 2 |  | 0
2010-04-17 05:00 | Clean & Clear Rig Floor | 0 | 0.5 |  | 0
2010-04-17 05:30 |  | 0 |  |  | 0
2010-04-17 05:30 |  |  | 0
2010-04-17 05:30 | DIMS PHASE: ABAN (Suspend)
2010-04-17 05:30 | T&A WELL or Clean out Run & Prod Casing
2010-04-17 05:30 | OpenWells EVENT: COF PHASE: RUNPRD
2010-04-17 05:30 | Make up BHA and RIH for a Clean out trip prior to running casing
2010-04-17 05:30 | C&C POOH and Lay down BHA
2010-04-17 05:30 |  | 0 |  |  | 0
2010-04-17 05:30 | Run / Cmt 7" x 9-7/8" Casing
2010-04-17 05:30 | Safety Meeting on R/U Csg tools | 0 | 0.5 |  | 0
2010-04-17 06:00 | R/U Wft casing tools | 0 | 2.5 |  | 0
2010-04-17 08:30 | Pick up 7" Shoe Track | 0 | 1 |  | 0
2010-04-17 09:30 | Run 6,000' of 7" Casing (26 doubles) | 0 | 8 |  | 0
2010-04-17 17:30 | R.D 7" Tools & R/U 9 7/8" Tools | 0 | 1.5 |  | 0
2010-04-17 19:00 | Run 7,000' +/- 9 7/8" csg | 0 | 14 |  | 0
2010-04-18 09:00 | R/D Csg Elevator OES, R/U DP Elevator | 0 | 0.5 |  | 0
2010-04-18 09:30 | P/U Dril Quip Hanger | 0 | 1 |  | 0
2010-04-18 10:30 | RIH w/ 7" x 9 7/8" on 6 5/8" Landing String | 0 | 11 |  | 0
2010-04-18 21:30 | PU Cement head, C&C |  | 1
2010-04-18 22:30 | Land out hanger in W/H | 0 | 0.5 |  | 0
2010-04-18 23:00 | Perform Foam Cmt job | 0 | 5 |  | 0
2010-04-19 04:00 | Set Seal Assy & test | 0 | 1 |  | 0
2010-04-19 05:00 | Shear out of hanger | 0 | 0.5 |  | 0
2010-04-19 05:30 | POH W/ L/S & R/T | 0 | 2 |  | 0
2010-04-19 07:30 | L/D R/T | 0 | 0.5 |  | 0
2010-04-19 08:00 |  | 0 |  |  | 0
2010-04-19 08:00 | Lead Impression / Lock Down | 0 |  |  | 0
2010-04-19 08:00 | CLEAN RIG FLOOR AND C/O Rig Floor Equipment. |  | 1
2010-04-19 09:00 | MU Dril-Quip LIT on 6-5/8" landing string & TIH (PU extra DC or drillpipe for 100k weight below tool) | 0 | 12.5 |  | 0
2010-04-19 21:30 | Perform Impression Block Operation | 0 | 1.5 |  | 0
2010-04-19 23:00 | POOH w/LIT & LD LIT | 0 | 8 |  | 0
2010-04-20 07:00 | MU & GIH w/ lockdown sleeve on 6-5/8" landing string w/ drill collars or DP for 100k# below | 0 | 5 |  | 0
2010-04-20 12:00 | Engage Lockdown sleeve | 0 | 4 |  | 0
2010-04-20 16:00 | POOH & LD running tool & excess DC or dp | 0 | 9 |  | 0
2010-04-21 01:00 | M/U FASDRIL PACKER OR GT PLUG AND SETTING TOOL, M/U X-OVER AND PBL SUB ON 5 1/2" DP. |  | 1
2010-04-21 02:00 | RIH WITH FASDRIL PACKER OR GT PLUG TO +/- 8300'. |  | 5
2010-04-21 07:00 | FLOW CHECK WELL, WELL STATIC & SET HES FASDRIL PACKER or GT Plug |  | 2
2010-04-21 09:00 | Pressure test plug. POOH ~ 1400 ft |  | 2
2010-04-21 11:00 | POOH & LD setting tool |  | 8
2010-04-21 19:00 | Wireline / CBL Run | 0 |  |  | 0
2010-04-21 19:00 | Safety meeting on R/U Wireline & P/U Tools | 0 | 0.5 |  | 0
2010-04-21 19:30 | R/U Schlumberger Wireline | 0 | 1.5 |  | 0
2010-04-21 21:00 | Descent # 1 CBL | 0 | 8 |  | 0
2010-04-22 05:00 | L/D Tools | 0 | 0.5 |  | 0
2010-04-22 05:30 | R/D W/L | 0 | 1.5 |  | 0
2010-04-22 07:00 | Clear & Clean Rig Floor | 0 | 0.5 |  | 0
2010-04-22 07:30 |  | 0 |  |  | 0
2010-04-22 07:30 | DIMS PHASE: POST
2010-04-22 07:30 | P/U Riser brush assy | 0 | 1 |  | 0
2010-04-22 08:30 | TIH to 5,000' +/- | 0 |  |  | 0
2010-04-22 08:30 | Circ & Clean Riser | 0 |  |  | 0
2010-04-22 08:30 |  | 0 |  |  | 0
2010-04-22 08:30 | PULL BOP AND RISER
2010-04-22 08:30 | RU to handle riser, Unlatch riser, move to 50 ft from wellhead |  | 10
2010-04-22 18:30 | Pull BOP & Riser |  | 20
2010-04-23 14:30 | RD riser handling equipment. LD diverter running tool. |  | 6.5
2010-04-23 21:00 | Clean Mud System on rig |  | 72
2010-04-26 21:00 | End Of Well -Move To Nile |  | 24
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
2010-04-27 21:00
Formulas:
Macondo, MC 252 = IF([Actual Time, row above]>0,[Macondo, MC 252, row above]+[Actual Time, row above]/24,[Macondo, MC 252, row above]+[Daily Working Estimate, row above]/24)
Macondo, MC 252 = IF([Actual Operation Skipped (Y or N), row above]="y",[Macondo, MC 252, row above]+[Actual Time, row above]/24,IF([Actual Time, row above]>0,[Macondo, MC 252, row above]+[Actual Time, row above]/24,[Macondo, MC 252, row above]+[Daily Working Estimate, row above]/24))
Note on C5: Peter de Jong: This is the target team which the team developed at the TL workshop. This target time should not be modified during the well execution!!!
Note on D5: Peter de Jong: The daily working estimate can be used to finetune the forward plan and review its consequences. The daily working estimate will vary during the well execution.

## 5 Day Forecast
| 5 DAY OPERATIONAL FORECAST | [7 empty] | WELL : | Macondo, MC 252
2010-04-16 |  |  | 2010-04-17 |  |  | 2010-04-18 |  |  | 2010-04-19 |  |  | 2010-04-20
40284 | Stage up pumps & circ |  | 40285 | POH to BHA / Pull Wear Sleeve |  | 40286 | Run 7,000' +/- 9 7/8" csg |  | 40287 | Perform Foam Cmt job |  | 40288 | POOH w/LIT & LD LIT
40284.0417 | TIH to 18, 100' +/- |  | 40285.0417 |  |  | 40286.0417 |  |  | 40287.0417 |  |  | 40288.0417
40284.0834 | Wash to TD |  | 40285.0834 |  |  | 40286.0834 |  |  | 40287.0834 |  |  | 40288.0834
40284.1251 |  |  | 40285.1251 | L/D BHA |  | 40286.1251 |  |  | 40287.1251 |  |  | 40288.1251
40284.1667 | Pump sweep / C&C Mud |  | 40285.1667 |  |  | 40286.1667 |  |  | 40287.1667 | Set Seal Assy & test |  | 40288.1667
40284.2084 |  |  | 40285.2084 | Clean & Clear Rig Floor |  | 40286.2084 |  |  | 40287.2084 | Shear out of hanger |  | 40288.2084
40284.2501 |  |  | 40285.2501 | R/U Wft casing tools |  | 40286.2501 |  |  | 40287.2501 | POH W/ L/S & R/T |  | 40288.2501
40284.2918 |  |  | 40285.2918 |  |  | 40286.2918 |  |  | 40287.2918 |  |  | 40288.2918 | MU & GIH w/ lockdown sleeve on 6-5/8" landing string w/ drill collars or DP for 100k# below
40284.3335 |  |  | 40285.3335 |  |  | 40286.3335 |  |  | 40287.3335 | CLEAN RIG FLOOR AND C/O Rig Floor Equipment. |  | 40288.3335
40284.3752 |  |  | 40285.3752 | Pick up 7" Shoe Track |  | 40286.3752 | R/D Csg Elevator OES, R/U DP Elevator |  | 40287.3752 | MU Dril-Quip LIT on 6-5/8" landing string & TIH (PU extra DC or drillpipe for 100k weight below tool) |  | 40288.3752
40284.4168 |  |  | 40285.4168 | Run 6,000' of 7" Casing (26 doubles) |  | 40286.4168 | P/U Dril Quip Hanger |  | 40287.4168 |  |  | 40288.4168
40284.4585 |  |  | 40285.4585 |  |  | 40286.4585 | RIH w/ 7" x 9 7/8" on 6 5/8" Landing String |  | 40287.4585 |  |  | 40288.4585
40284.5002 | POH to BHA / Pull Wear Sleeve |  | 40285.5002 |  |  | 40286.5002 |  |  | 40287.5002 |  |  | 40288.5002 | Engage Lockdown sleeve
40284.5419 |  |  | 40285.5419 |  |  | 40286.5419 |  |  | 40287.5419 |  |  | 40288.5419
40284.5836 |  |  | 40285.5836 |  |  | 40286.5836 |  |  | 40287.5836 |  |  | 40288.5836
40284.6253 |  |  | 40285.6253 |  |  | 40286.6253 |  |  | 40287.6253 |  |  | 40288.6253
40284.6669 |  |  | 40285.6669 |  |  | 40286.6669 |  |  | 40287.6669 |  |  | 40288.6669 | POOH & LD running tool & excess DC or dp
40284.7086 |  |  | 40285.7086 |  |  | 40286.7086 |  |  | 40287.7086 |  |  | 40288.7086
40284.7503 |  |  | 40285.7503 | R.D 7" Tools & R/U 9 7/8" Tools |  | 40286.7503 |  |  | 40287.7503 |  |  | 40288.7503
40284.792 |  |  | 40285.792 | Run 7,000' +/- 9 7/8" csg |  | 40286.792 |  |  | 40287.792 |  |  | 40288.792
40284.8337 |  |  | 40285.8337 |  |  | 40286.8337 |  |  | 40287.8337 |  |  | 40288.8337
40284.8754 |  |  | 40285.8754 |  |  | 40286.8754 |  |  | 40287.8754 |  |  | 40288.8754
40284.917 |  |  | 40285.917 |  |  | 40286.917 | PU Cement head, C&C |  | 40287.917 | Perform Impression Block Operation |  | 40288.917
40284.9587 |  |  | 40285.9587 |  |  | 40286.9587 | Perform Foam Cmt job |  | 40287.9587 | POOH w/LIT & LD LIT |  | 40288.9587
| Equipment From Rig |  |  | Equipment From Rig |  |  | Equipment From Rig |  |  | Equipment From Rig |  |  | Equipment From Rig
Weatherford OMNI | [8 empty] | Halliburton N2 Equipment |  |  | Halliburton N2 Equipment
Smith Fishing Kit | [8 empty] | Weatherford Csg Tools |  |  | Weatherford Csg Tools
Schlumberger Logging | [8 empty] | Excess casing |  |  | Excess casing
| Equipment To Rig |  |  | Equipment To Rig |  |  | Equipment To Rig |  |  | Equipment To Rig |  |  | Equipment To Rig
Schlumberger CBL Tools | [5 empty] | Transocean - Tensioner
Dril Quip Hanger | [5 empty] | TOI - Tensioner Tool
MI Riser brush assy | [5 empty] | Above Items Stored in Fourchon
MI Clean out Chemicals
Groceries
| (To Rig) CREWCHANGE (From Rig) |  |  | (To Rig) CREWCHANGE (From Rig) |  |  | (To Rig) CREWCHANGE (From Rig) |  |  | (To Rig) CREWCHANGE (From Rig) |  |  | (To Rig) CREWCHANGE (From Rig)
8 | Transocean | 8 | [6 empty] | 4 | Art Catering | 4 | 2 | MI Compliance / Mud | 2
2 | Bp ( WSL ) | 1 |  |  |  |  | No Flight Planned |  | 1 | Bp I.T. | 1 | 1 | Halliburton Cmt | 1
| Cleanblast | 4 | [6 empty] | 2 | Oceaneering | 2 | 3 | Sperry (Mud Log, DD, MWD) | 3
2 | MI Completion / Sperry | 2 | [6 empty] | 3 | Transocean | 3 | 1 | Weatherford
3 | Bp Intervention Subsea | [7 empty] | 3 | Schlumberger CBL |  |  | Bp I.T. | 1
2 | Offshore Clean
4 | Halliburton N2
2 | Weatherford Csg | [11 empty] | 2nd Flight *VIP
[12 empty] | 2 | Bp
[12 empty] | 2 | TOI
23 |  | 15 | 0 |  | 0 | 0 |  | 0 | 13 |  | 10 | 11 |  | 7
Max. Pers. |  | 146 |  | Yesterday's POB | 137 |  | Max forecast POB next 5 days | 152
POB |  | 145 | POB |  | 145 | POB |  | 145 | POB |  | 148 | POB |  | 152
Vessels |  |  | Vessels |  |  | Vessels |  |  | Vessels |  |  | Vessels
| Damon Bankston load Fourchon |  |  | Damon Bankston at rig |  |  | Damon Bankston at rig |  |  | Damon Bankston at rig |  |  | Damon Bankston at rig
| C-Express Transits to Fourchon |  |  | C-Express at Fourchon Load
2010-04-16 |  |  | 2010-04-17 |  |  | 2010-04-18 |  |  | 2010-04-19 |  |  | 2010-04-20
| Next BOP Test Due |  |  | Next Casing Test Due |  |  | Next Casing Caliper Due
'Operations Input'!A564 | 2010-04-24 06:00 |  | 'Operations Input'!A496 | 2010-05-01 12:30 |  | 'Operations Input'!A5 | #VALUE!
Formulas:
Vessels = [Vessels]+1
Equipment From Rig = INDIRECT([Vessels])+14

## 10 Day Forecast
| 10 DAY OPERATIONAL FORECAST |  |  |  |  | WELL : | Macondo, MC 252
2010-04-16 |  | 2010-04-17 |  | 2010-04-18 |  | 2010-04-19 |  | 2010-04-20
40284 | Stage up pumps & circ | 40285 | POH to BHA / Pull Wear Sleeve | 40286 | Run 7,000' +/- 9 7/8" csg | 40287 | Perform Foam Cmt job | 40288 | POOH w/LIT & LD LIT
40284.0417 | TIH to 18, 100' +/- | 40285.0417 |  | 40286.0417 |  | 40287.0417 |  | 40288.0417
40284.0834 | Wash to TD | 40285.0834 |  | 40286.0834 |  | 40287.0834 |  | 40288.0834
40284.1251 |  | 40285.1251 | L/D BHA | 40286.1251 |  | 40287.1251 |  | 40288.1251
40284.1667 | Pump sweep / C&C Mud | 40285.1667 |  | 40286.1667 |  | 40287.1667 | Set Seal Assy & test | 40288.1667
40284.2084 |  | 40285.2084 | Clean & Clear Rig Floor | 40286.2084 |  | 40287.2084 | Shear out of hanger | 40288.2084
40284.2501 |  | 40285.2501 | R/U Wft casing tools | 40286.2501 |  | 40287.2501 | POH W/ L/S & R/T | 40288.2501
40284.2918 |  | 40285.2918 |  | 40286.2918 |  | 40287.2918 |  | 40288.2918 | MU & GIH w/ lockdown sleeve on 6-5/8" landing string w/ drill collars or DP for 100k# below
40284.3335 |  | 40285.3335 |  | 40286.3335 |  | 40287.3335 | CLEAN RIG FLOOR AND C/O Rig Floor Equipment. | 40288.3335
40284.3752 |  | 40285.3752 | Pick up 7" Shoe Track | 40286.3752 | R/D Csg Elevator OES, R/U DP Elevator | 40287.3752 | MU Dril-Quip LIT on 6-5/8" landing string & TIH (PU extra DC or drillpipe for 100k weight below tool) | 40288.3752
40284.4168 |  | 40285.4168 | Run 6,000' of 7" Casing (26 doubles) | 40286.4168 | P/U Dril Quip Hanger | 40287.4168 |  | 40288.4168
40284.4585 |  | 40285.4585 |  | 40286.4585 | RIH w/ 7" x 9 7/8" on 6 5/8" Landing String | 40287.4585 |  | 40288.4585
40284.5002 | POH to BHA / Pull Wear Sleeve | 40285.5002 |  | 40286.5002 |  | 40287.5002 |  | 40288.5002 | Engage Lockdown sleeve
40284.5419 |  | 40285.5419 |  | 40286.5419 |  | 40287.5419 |  | 40288.5419
40284.5836 |  | 40285.5836 |  | 40286.5836 |  | 40287.5836 |  | 40288.5836
40284.6253 |  | 40285.6253 |  | 40286.6253 |  | 40287.6253 |  | 40288.6253
40284.6669 |  | 40285.6669 |  | 40286.6669 |  | 40287.6669 |  | 40288.6669 | POOH & LD running tool & excess DC or dp
40284.7086 |  | 40285.7086 |  | 40286.7086 |  | 40287.7086 |  | 40288.7086
40284.7503 |  | 40285.7503 | R.D 7" Tools & R/U 9 7/8" Tools | 40286.7503 |  | 40287.7503 |  | 40288.7503
40284.792 |  | 40285.792 | Run 7,000' +/- 9 7/8" csg | 40286.792 |  | 40287.792 |  | 40288.792
40284.8337 |  | 40285.8337 |  | 40286.8337 |  | 40287.8337 |  | 40288.8337
40284.8754 |  | 40285.8754 |  | 40286.8754 |  | 40287.8754 |  | 40288.8754
40284.917 |  | 40285.917 |  | 40286.917 | PU Cement head, C&C | 40287.917 | Perform Impression Block Operation | 40288.917
40284.9587 |  | 40285.9587 |  | 40286.9587 | Perform Foam Cmt job | 40287.9587 | POOH w/LIT & LD LIT | 40288.9587
2010-04-21 |  | 2010-04-22 |  | 2010-04-23 |  | 2010-04-24 |  | 2010-04-25
40289 | POOH & LD running tool & excess DC or dp | 40290 | Descent # 1 CBL | 40291 | Pull BOP & Riser | 40292 | Clean Mud System on rig | 40293 | Clean Mud System on rig
40289.0417 | M/U FASDRIL PACKER OR GT PLUG AND SETTING TOOL, M/U X-OVER AND PBL SUB ON 5 1/2" DP. | 40290.0417 |  | 40291.0417 |  | 40292.0417 |  | 40293.0417
40289.0834 | RIH WITH FASDRIL PACKER OR GT PLUG TO +/- 8300'. | 40290.0834 |  | 40291.0834 |  | 40292.0834 |  | 40293.0834
40289.1251 |  | 40290.1251 |  | 40291.1251 |  | 40292.1251 |  | 40293.1251
40289.1667 |  | 40290.1667 |  | 40291.1667 |  | 40292.1667 |  | 40293.1667
40289.2084 |  | 40290.2084 | L/D Tools | 40291.2084 |  | 40292.2084 |  | 40293.2084
40289.2501 |  | 40290.2501 | R/D W/L | 40291.2501 |  | 40292.2501 |  | 40293.2501
40289.2918 | FLOW CHECK WELL, WELL STATIC & SET HES FASDRIL PACKER or GT Plug | 40290.2918 | Clear & Clean Rig Floor | 40291.2918 |  | 40292.2918 |  | 40293.2918
40289.3335 |  | 40290.3335 | P/U Riser brush assy | 40291.3335 |  | 40292.3335 |  | 40293.3335
40289.3752 | Pressure test plug. POOH ~ 1400 ft | 40290.3752 | RU to handle riser, Unlatch riser, move to 50 ft from wellhead | 40291.3752 |  | 40292.3752 |  | 40293.3752
40289.4168 |  | 40290.4168 |  | 40291.4168 |  | 40292.4168 |  | 40293.4168
40289.4585 | POOH & LD setting tool | 40290.4585 |  | 40291.4585 |  | 40292.4585 |  | 40293.4585
40289.5002 |  | 40290.5002 |  | 40291.5002 |  | 40292.5002 |  | 40293.5002
40289.5419 |  | 40290.5419 |  | 40291.5419 |  | 40292.5419 |  | 40293.5419
40289.5836 |  | 40290.5836 |  | 40291.5836 |  | 40292.5836 |  | 40293.5836
40289.6253 |  | 40290.6253 |  | 40291.6253 | RD riser handling equipment. LD diverter running tool. | 40292.6253 |  | 40293.6253
40289.6669 |  | 40290.6669 |  | 40291.6669 |  | 40292.6669 |  | 40293.6669
40289.7086 |  | 40290.7086 |  | 40291.7086 |  | 40292.7086 |  | 40293.7086
40289.7503 |  | 40290.7503 |  | 40291.7503 |  | 40292.7503 |  | 40293.7503
40289.792 | Safety meeting on R/U Wireline & P/U Tools | 40290.792 | Pull BOP & Riser | 40291.792 |  | 40292.792 |  | 40293.792
40289.8337 | R/U Schlumberger Wireline | 40290.8337 |  | 40291.8337 |  | 40292.8337 |  | 40293.8337
40289.8754 | Descent # 1 CBL | 40290.8754 |  | 40291.8754 | Clean Mud System on rig | 40292.8754 |  | 40293.8754
40289.917 |  | 40290.917 |  | 40291.917 |  | 40292.917 |  | 40293.917
40289.9587 |  | 40290.9587 |  | 40291.9587 |  | 40292.9587 |  | 40293.9587

## Crew Change
Yesterdays POB | 137
Date | ON | Name # 1 | OFF | ON | Name # 2 | OFF | ON | Name # 3 | OFF | ON | Name # 4 | OFF | ON | Name # 5 | OFF | ON | Name # 6 | OFF | ON | Name # 7 | OFF | ON | Name # 8 | OFF | ON | Name # 9 | OFF | ON | Name # 10 | OFF | ON | Name # 11 | OFF | ON | Name # 12 | OFF
2010-01-31
2010-02-01
2010-02-02
2010-02-03
2010-02-04
2010-02-05
2010-02-06
2010-02-07
2010-02-08
2010-02-09
2010-02-10
2010-02-11
2010-02-12
2010-02-13
2010-02-14
2010-02-15
2010-02-16
2010-02-17
2010-02-18
2010-02-19
2010-02-20
2010-02-21
2010-02-22
2010-02-23
2010-02-24
2010-02-25
2010-02-26
2010-02-27
2010-02-28
2010-03-01
2010-03-02
2010-03-03
2010-03-04
2010-03-05
2010-03-06
2010-03-07
2010-03-08
2010-03-09
2010-03-10
2010-03-11
2010-03-12
2010-03-13
2010-03-14
2010-03-15
2010-03-16
2010-03-17
2010-03-18
2010-03-19
2010-03-20
2010-03-21
2010-03-22
2010-03-23
2010-03-24
2010-03-25
2010-03-26
2010-03-27
2010-03-28
2010-03-29 | 4 | Transocean | 4 | 5 | Art | 5 | 3 | Bp | 1 | 2 | MI Swaco | 2 | 1 | Oceaneering | 1 | 2 | Sperry / Allamon | 1 | 1 | Haliburton |  | 3 | Weatherford |  | 2 | OES / Hydril |  |  | Definitions / Hampco | 2
2010-03-30 | 2 | Transocean | 6 | 3 | Bp | 4 |  | Weatherford | 1 | 1 | Sperry Logger | 2 |  | AKA | 2 | 1 | ART Catering
2010-03-31 | 1 | Performance Coordinator | 1 | 1 | Halliburton Cmt | 1 | 1 | MI Swaco | 1 | 1 | Sperry | 1 | 1 | Baker | 1 | 5 | Ellington Pale |  | 13 | Transocean | 15 | 3 | Bp | 1 | 1 | Weatherford Csg | 1
2010-04-01 | 14 | Transocean | 11 | 4 | ModuSpec |  | 1 | Hiller |  |  | Bp | 2 |  | Halliburton | 1 |  | Weatherford | 2 |  | OES / Hydrill | 2 |  | Allamon | 1 |  | Blackhawk | 1 | 1 | Sperry
2010-04-02 | 9 | Transocean | 9 | 1 | ModuSpec |  | 1 | Cleanblast |  |  | ART | 1
2010-04-03 |  |  |  |  | No Flight Planned
2010-04-04 |  |  |  |  | No Flight Planned
2010-04-05 | 6 | ART | 4 | 1 | Transocean | 1 | 1 | MI Swaco | 1 | 1 | Sperry | 1 | 2 | Oceaneering | 2 | 1 | Hiller |  | 1 | NOV |  | 2 | Schlumberger
2010-04-06 | 1 | EPS | 1 | 1 | MI |  | 1 | Halliburton | 1 | 3 | Sperry (Mud Log, DD, MWD) | 3 | 2 | Sperry (SC) | 2 |  | NOV / Hiller | 2 |  | Paleo / SC/ Pore (?) | 11 |  |  |  | 6 | Schlumberger (?) |  | 1 | Smith (?)
2010-04-07 | 1 | Bp WSL | 1
2010-04-08 | 1 | QO (geologist) | 1 | 2 | Total Safety |  |  | Sperry ( DD) | 1 |  | Pro-Log | 1 | 2 | Schlumberger |  |  | BHI ( Reamer) | 1
2010-04-09 | 5 | Schlumberger |  | 1 | Impact Selector |  | 1 | Smith Fishing |  | 1 | BP (Galina) |  |  | QO ( Pore Pressure) | 1 | 1 | OilPhase |  | 1 | Tidewater | 1
2010-04-10 | 4 | Pencor |  |  | Sperry ( SC) | 1 |  | Transocean | 1 |  | MI ( Mud) | 1
2010-04-11 | 3 | Schlumberger ( Seismic / MST) |  |  | Sperry ( SC) | 1 |  | Transocean | 1 |  | BP ( WSLfd) | 1
2010-04-12 | 4 | Art Catering | 4 |  | Sperry ( MWD) | 2 | 1 | MI Swaco | 1 | 3 | Transocean | 4 | 3 | Geocet (MMO) |  | 1 | Weatherford Labs |  |  | Moduspec | 4 | 2 | Schlumberger |  | 1 | Dril Quip
2010-04-13 | 1 | BP ( Performance) | 1 | 1 | MI (Mud) | 0 | 2 | Halliburton / Weatherford | 2 | 3 | Sperry ( DD/ MWD/ML) | 2 | 2 | Transocean | 2 |  | Total safety | 2 | 1 | LaMaritime |  |  | Impact Selector | 1 |  | Schlumberger | 1
2010-04-14 | 1 | BP (WSL) | 1 | 16 | Transocean | 15 |  | BP (Galina) | 1 | 1 | Schlumberger |  |  | 2nd Flight-PM |  | 1 | Protechnics |  | 1 | Schlumberger | 4 |  | Pencor | 4 |  | Transocean | 1
2010-04-15 | 9 | Transocean | 11 | 1 | LEM |  | 6 | OCS ( Cleaning ) |  |  | LaMaritime / LEM | 2 |  | 2nd Flight-PM |  | 1 | BP Eng / QO Geol | 1 | 4 | OES / Hydrill/ Smith Fish | 1 | 4 | Weatherford Csg |  | 2 | Allamon / Blackhawk |  |  | SLB W.L. / MMO | 13
2010-04-16 | 8 | Transocean | 8 | 2 | Bp ( WSL ) | 1 |  | Cleanblast | 4 | 2 | MI Completion / Sperry | 2 | 3 | Bp Intervention Subsea |  | 2 | Offshore Clean |  | 4 | Halliburton N2 |  | 2 | Weatherford Csg
2010-04-17
2010-04-18 |  |  |  |  | No Flight Planned
2010-04-19 | 4 | Art Catering | 4 | 1 | Bp I.T. | 1 | 2 | Oceaneering | 2 | 3 | Transocean | 3 | 3 | Schlumberger CBL
2010-04-20 | 2 | MI Compliance / Mud | 2 | 1 | Halliburton Cmt | 1 | 3 | Sperry (Mud Log, DD, MWD) | 3 | 1 | Weatherford |  |  | Bp I.T. | 1 | [7 empty] | 2nd Flight *VIP |  | 2 | Bp |  | 2 | TOI
2010-04-21 | 1 | Bp WSL | 1 | 17 | Transocean | 17 | [16 empty] | 2nd Flight *VIP |  |  | Bp | 2 |  | TOI | 1
2010-04-22 | 10 | Transocean | 10
2010-04-23 | 1 | EPS / Woodgroup | 1 | 5 | Transocean | 5
2010-04-24 |  |  |  |  | No Flight Planned
2010-04-25 |  |  |  |  | No Flight Planned
2010-04-26
2010-04-27
2010-04-28
2010-04-29
2010-04-30
2010-05-01 |  |  |  |  | No Flight Planned
2010-05-02 |  |  |  |  | No Flight Planned
2010-05-03
2010-05-04
2010-05-05
2010-05-06
2010-05-07
2010-05-08 |  |  |  |  | No Flight Planned
2010-05-09 |  |  |  |  | No Flight Planned
2010-05-10
2010-05-11
2010-05-12
2010-05-13
2010-05-14
2010-05-15 |  |  |  |  | No Flight Planned
2010-05-16 |  |  |  |  | No Flight Planned
2010-05-17
2010-05-18
2010-05-19
2010-05-20
2010-05-21
2010-05-22 |  |  |  |  | No Flight Planned
2010-05-23 |  |  |  |  | No Flight Planned
2010-05-24
2010-05-25
2010-05-26
2010-05-27
2010-05-28
2010-05-29 |  |  |  |  | No Flight Planned
2010-05-30 |  |  |  |  | No Flight Planned
2010-05-31
2010-06-01
2010-06-02
2010-06-03
2010-06-04
2010-06-05 |  |  |  |  | No Flight Planned
2010-06-06 |  |  |  |  | No Flight Planned
2010-06-07
2010-06-08
2010-06-09
2010-06-10
2010-06-11
2010-06-12 |  |  |  |  | No Flight Planned
2010-06-13 |  |  |  |  | No Flight Planned
2010-06-14
2010-06-15
2010-06-16
2010-06-17
2010-06-18
2010-06-19
2010-06-20
2010-06-21
2010-06-22
2010-06-23
2010-06-24
2010-06-25
2010-06-26
2010-06-27
2010-06-28
2010-06-29
2010-06-30
2010-07-01
2010-07-02
2010-07-03
2010-07-04
2010-07-05
2010-07-06
2010-07-07
2010-07-08
2010-07-09
2010-07-10
2010-07-11
2010-07-12
2010-07-13
2010-07-14
2010-07-15
2010-07-16
2010-07-17
2010-07-18
2010-07-19
2010-07-20
2010-07-21
2010-07-22
2010-07-23
2010-07-24
2010-07-25
2010-07-26
2010-07-27
2010-07-28
2010-07-29
2010-07-30
2010-07-31
2010-08-01
2010-08-02
2010-08-03
2010-08-04
2010-08-05
2010-08-06
2010-08-07
2010-08-08
2010-08-09
2010-08-10
2010-08-11
2010-08-12
2010-08-13
2010-08-14
2010-08-15
2010-08-16
2010-08-17
2010-08-18
2010-08-19
2010-08-20
2010-08-21
2010-08-22
2010-08-23
2010-08-24
2010-08-25
2010-08-26
2010-08-27
2010-08-28
2010-08-29
2010-08-30
2010-08-31
2010-09-01
2010-09-02
2010-09-03
2010-09-04
2010-09-05
2010-09-06
2010-09-07
2010-09-08
2010-09-09
2010-09-10
2010-09-11
2010-09-12
2010-09-13
2010-09-14
2010-09-15
2010-09-16
2010-09-17
2010-09-18
2010-09-19
2010-09-20
2010-09-21
2010-09-22
2010-09-23
2010-09-24
2010-09-25
2010-09-26
2010-09-27
2010-09-28
2010-09-29
2010-09-30
2010-10-01
2010-10-02
2010-10-03
2010-10-04
2010-10-05
2010-10-06
2010-10-07
2010-10-08
2010-10-09
2010-10-10
2010-10-11
2010-10-12
2010-10-13
2010-10-14
2010-10-15
2010-10-16
2010-10-17
2010-10-18
2010-10-19
2010-10-20
2010-10-21
2010-10-22
2010-10-23
2010-10-24
2010-10-25
2010-10-26
2010-10-27
2010-10-28
2010-10-29
2010-10-30
2010-10-31
2010-11-01
2010-11-02
2010-11-03
2010-11-04
2010-11-05
2010-11-06
2010-11-07
2010-11-08
2010-11-09
2010-11-10
2010-11-11
2010-11-12
2010-11-13
2010-11-14
2010-11-15
2010-11-16
2010-11-17
2010-11-18
2010-11-19
2010-11-20
2010-11-21
2010-11-22
2010-11-23
2010-11-24
2010-11-25
2010-11-26
2010-11-27
2010-11-28
2010-11-29
2010-11-30
2010-12-01
2010-12-02
2010-12-03
2010-12-04
2010-12-05
2010-12-06
2010-12-07
2010-12-08
2010-12-09
2010-12-10
2010-12-11
2010-12-12
2010-12-13
2010-12-14
2010-12-15
2010-12-16
2010-12-17
2010-12-18
2010-12-19
2010-12-20
2010-12-21
2010-12-22
2010-12-23
2010-12-24
2010-12-25
2010-12-26
2010-12-27
2010-12-28
2010-12-29
2010-12-30
2010-12-31
2011-01-01
2011-01-02
2011-01-03
2011-01-04
2011-01-05
2011-01-06
2011-01-07
2011-01-08
2011-01-09
2011-01-10
2011-01-11
2011-01-12
2011-01-13
2011-01-14
2011-01-15
2011-01-16
2011-01-17
2011-01-18
2011-01-19
2011-01-20
2011-01-21
2011-01-22
2011-01-23
2011-01-24
2011-01-25
2011-01-26
2011-01-27
2011-01-28
2011-01-29
2011-01-30
2011-01-31
2011-02-01
2011-02-02
2011-02-03
2011-02-04
2011-02-05
2011-02-06
2011-02-07
2011-02-08
2011-02-09
2011-02-10
2011-02-11
2011-02-12
2011-02-13
2011-02-14
2011-02-15
2011-02-16
2011-02-17
2011-02-18
2011-02-19
2011-02-20
2011-02-21
2011-02-22
2011-02-23
2011-02-24
2011-02-25
Formulas:
Date = [Date, row above]+1

## Boat Input
Date | Equipment FROM Rig | [6 empty] | Equipment TO Rig | [7 empty] | Vessels # 1 | Vessels # 2 | Vessels # 3
2010-01-31
2010-02-01
2010-02-02
2010-02-03
2010-02-04
2010-02-05
2010-02-06
2010-02-07
2010-02-08
2010-02-09
2010-02-10
2010-02-11
2010-02-12
2010-02-13
2010-02-14
2010-02-15
2010-02-16
2010-02-17
2010-02-18
2010-02-19
2010-02-20
2010-02-21
2010-02-22
2010-02-23
2010-02-24
2010-02-25
2010-02-26
2010-02-27
2010-02-28
2010-03-01
2010-03-02
2010-03-03
2010-03-04
2010-03-05
2010-03-06
2010-03-07
2010-03-08
2010-03-09
2010-03-10
2010-03-11
2010-03-12
2010-03-13
2010-03-14
2010-03-15
2010-03-16
2010-03-17
2010-03-18
2010-03-19
2010-03-20
2010-03-21
2010-03-22
2010-03-23
2010-03-24
2010-03-25
2010-03-26
2010-03-27
2010-03-28
2010-03-29 | [7 empty] | Halliburton L/H | Weatherford Cmt Wiper Plugs | Allamon Diverter | Hydril Lift Nubbins & X/Over | Weatherford 9 7/8 Tools | Mi- Chem Order |  | 5000 sxs Barite | M/V Damon Bankston At Rig
2010-03-30 | [7 empty] | 8" Geo Tap Back Up, | Empty Pallet Boxes | Mudlog Samples | Allamon Diverter |  |  |  |  | M/V Damon Bankston To Fourchon
2010-03-31 | [7 empty] | 8 1/2" Bits For Next Section | Oceaneering Supplies | [6 empty] | M/V Damon Bankston At Fourchon | Fast Cajun InRoute To Horizon
2010-04-01 | [7 empty] | TOI - Total Safety Box | MI Swaco - Chemical Order | TOI - L&L Drums | Transocean Cargo Box | ART Catering Groceries | Sperry MWD Tool (For Swap) |  |  | M/V Damon Bankston at Rig
2010-04-02 | Blackhawk Equipment | Allamon Equipment | Halliburton Versa-Flex Equipment | Sperry Drilling Geo-Pilot Swap out | Full Cutting Box | B/U Float Equipment | B/U Wiper Plugs | [8 empty] | M/V Damon Bankston To Fourchon
2010-04-03 | [15 empty] | M/V Damon Bankston At Fourchon
2010-04-04 | (CB) Rental 6 5/8" HWDP | (CB)Rental 8 1/4 DC | (CB)TOI DC |  |  |  |  | Schlumberger W/L Tools | Smith Wireline Fishing Tools | Pencor Equipent | [5 empty] | Damon Bankston to Rig | Sailfish
2010-04-05 | [7 empty] | 2000 bbls base oil | MI - LCM | [6 empty] | Damon Bankston at Rig O/L | HOS Silver Arrow
2010-04-06 | [15 empty] | Damon Bankston to dock
2010-04-07 | [7 empty] | Schlumberger Logging Tools | Pencor equip. | Smith Fishing kit | 3000 bbls 14.0 Mud | 5000 barite | MI LCM | Turbo Chem -EZ Squeeze |  | Damon Bankston Loading
2010-04-08 | [7 empty] | Groceries | Rig Supplies | [6 empty] | Damon Bankston To Rig | Crew Boat
2010-04-09 | [15 empty] | Damon Bankston at rig O/L
2010-04-10 | [15 empty] | Damon Bankston to Fourchon PM
2010-04-11 | [7 empty] | 6,147' - 7", Q-125 Hydril 513 Csg | 7,000' - 9 7/8",HCQ125, Hyd 523 Csg | Allamon Diverter / Blackhawk Cmt Head | Wft / Hydril 9 7/8 & 7" Csg Tools | OES Flow Back Tools | Crewboat - Schlumberger MSCT Tools |  |  | Damon Bankston Fou / Loading | Crewboat -MDT Tools
2010-04-12 | [15 empty] | Damon Bankston to Rig | C-Express - Fouchon Loading
2010-04-13 | [7 empty] | C-Express -Dril-Quip Hangers | C-Express -OCS-Cleaning Equip | C-Express -Halliburton Foam Equip. | C-Express -( 1 ) 7" x 9 7/8" X-Over Jt | C-Express -A/C X-Overs | C-Express -Protechnics ( PiP tags) |  | Crewboat -( 8 ) TOI 6 1/2" Collars | Damon Bankston at Rig O/L | C-Express to rig
2010-04-14 | Sperry Samples | Schlumberger Tools / Equip | Pencor Equip | Weatherford Labs | Smith Fishing Kit |  |  | B/U - 7" x 9 7/8" X-Over Jt | SLB Tools | B/U Drill pipe darts | [5 empty] | Damon Bankston at rig B/L | C-Express at rig
2010-04-15 | Pencor Equipment | Prolog Shack | Schlumberger Seismic Equipment |  |  | 5400 bbls 14.0 ppg SBM |  | Schlumberger CBL Tools | Dril Quip Hanger | MI Riser brush assy | MI Clean out Chemicals | Groceries |  |  |  | Damon Bankston to Fourchon | C-Express at rig
2010-04-16 | Weatherford OMNI | Smith Fishing Kit | Schlumberger Logging |  |  |  |  | Schlumberger CBL Tools | Dril Quip Hanger | MI Riser brush assy | MI Clean out Chemicals | Groceries |  |  |  | Damon Bankston load Fourchon | C-Express Transits to Fourchon
2010-04-17 | [15 empty] | Damon Bankston at rig | C-Express at Fourchon Load
2010-04-18 | [7 empty] | Transocean - Tensioner | TOI - Tensioner Tool | Above Items Stored in Fourchon | [5 empty] | Damon Bankston at rig
2010-04-19 | Halliburton N2 Equipment | Weatherford Csg Tools | Excess casing | [12 empty] | Damon Bankston at rig
2010-04-20 | Halliburton N2 Equipment | Weatherford Csg Tools | Excess casing | [12 empty] | Damon Bankston at rig
2010-04-21 | [15 empty] | Damon Bankston to Fourchon
2010-04-22 | [7 empty] | Groceries
2010-04-23
2010-04-24 | [7 empty] | Transocean Drill Line Spool | Transocean Drill Line Spooler
2010-04-25
2010-04-26
2010-04-27
2010-04-28
2010-04-29
2010-04-30
2010-05-01
2010-05-02
2010-05-03
2010-05-04
2010-05-05
2010-05-06
2010-05-07
2010-05-08
2010-05-09
2010-05-10
2010-05-11
2010-05-12
2010-05-13
2010-05-14
2010-05-15
2010-05-16
2010-05-17
2010-05-18
2010-05-19
2010-05-20
2010-05-21
2010-05-22
2010-05-23
2010-05-24
2010-05-25
2010-05-26
2010-05-27
2010-05-28
2010-05-29
2010-05-30
2010-05-31
2010-06-01
2010-06-02
2010-06-03
2010-06-04
2010-06-05
2010-06-06
2010-06-07
2010-06-08
2010-06-09
2010-06-10
2010-06-11
2010-06-12
2010-06-13
2010-06-14
2010-06-15
2010-06-16
2010-06-17
2010-06-18
2010-06-19
2010-06-20
2010-06-21
2010-06-22
2010-06-23
2010-06-24
2010-06-25
2010-06-26
2010-06-27
2010-06-28
2010-06-29
2010-06-30
2010-07-01
2010-07-02
2010-07-03
2010-07-04
2010-07-05
2010-07-06
2010-07-07
2010-07-08
2010-07-09
2010-07-10
2010-07-11
2010-07-12
2010-07-13
2010-07-14
2010-07-15
2010-07-16
2010-07-17
2010-07-18
2010-07-19
2010-07-20
2010-07-21
2010-07-22
2010-07-23
2010-07-24
2010-07-25
2010-07-26
2010-07-27
2010-07-28
2010-07-29
2010-07-30
2010-07-31
2010-08-01
2010-08-02
2010-08-03
2010-08-04
2010-08-05
2010-08-06
2010-08-07
2010-08-08
2010-08-09
2010-08-10
2010-08-11
2010-08-12
2010-08-13
2010-08-14
2010-08-15
2010-08-16
2010-08-17
2010-08-18
2010-08-19
2010-08-20
2010-08-21
2010-08-22
2010-08-23
2010-08-24
2010-08-25
2010-08-26
2010-08-27
2010-08-28
2010-08-29
2010-08-30
2010-08-31
2010-09-01
2010-09-02
2010-09-03
2010-09-04
2010-09-05
2010-09-06
2010-09-07
2010-09-08
2010-09-09
2010-09-10
2010-09-11
2010-09-12
2010-09-13
2010-09-14
2010-09-15
2010-09-16
2010-09-17
2010-09-18
2010-09-19
2010-09-20
2010-09-21
2010-09-22
2010-09-23
2010-09-24
2010-09-25
2010-09-26
2010-09-27
2010-09-28
2010-09-29
2010-09-30
2010-10-01
2010-10-02
2010-10-03
2010-10-04
2010-10-05
2010-10-06
2010-10-07
2010-10-08
2010-10-09
2010-10-10
2010-10-11
Formulas:
Date = [Date, row above]+1

## Hole Section Data
| Variance Log |  | P10??
|  | AFE | Target | Actual | Cumulative | Cumulative | Cumulative | Actual | Actual | Days ahead | Cum Days | Days ahead
| Operation | Time | Time | Time | AFE Time | Target Time | Actual Time | Start Time | End Time | vs. AFE | ahead vs AFE | vs. target
1 | Run & Cement 18" Casing - Drill Out - Perform LOT | 4.6 | 2.9 | #REF! | 4.6 | 2.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | Hurricane | 0 | 0 | #REF! | 4.6 | 2.9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | Drill 16-1/2" x 20" Hole Section | 3.8 | 2.4 | #REF! | 8.4 | 5.3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | Run & Cement 16" Casing - Perform LOT | 4.5 | 2.9 | #REF! | 12.9 | 8.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Drill 14-3/4" x 16-1/2" Hole Section | 3.8 | 2.4 | #REF! | 16.7 | 10.6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Run & Cement 13-5/8" Liner - Drill Out - Perform LOT | 5.5 | 3.4 | #REF! | 22.2 | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
7 | Drill 12-1/2" x 14" Hole Section | 4.3 | 3.2 | #REF! | 26.5 | 17.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | Contingency Run Expandable Liner 11-7/8" x 13-5/8" | 3.7 | 0 | #REF! | 30.2 | 17.2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | Drill 10-5/8" x 12-1/4" Hole Section | 4.2 | 3.2 | #REF! | 34.4 | 20.4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Evaluate Production Hole Section (WL) | 6.2 | 3.4
| Temporary Abandonment | 3.7 | 3
| Pull BOP | 3.7 | 3.3
| TOTALS : | 44.3 | 26.8 | #REF!
| Totals in hours | 1063.2 | 643.2 | #REF!
|  | AFE | Target | Actual | Cumulative | Cumulative | Cumulative | Planned | Planned | Planned | Planned | Planned | Planned | Target Band (AFE-Target)
| Operation | Time | Time | Time | AFE Time | Target Time | Actual Time | Start Time | End Time | Start Time | End Time | Start Time | End Time | (days)
[8 empty] | Team Targets |  | AFE |  | ACTUAL
1 | Run & Cement 18" Casing - Drill Out - Perform LOT | 4.6 | 2.9 | #REF! | 4.6 | 2.9 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 1.7
2 | Hurricane | 0 | 0 | #REF! | 4.6 | 2.9 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 1.7
3 | Drill 16-1/2" x 20" Hole Section | 3.8 | 2.4 | #REF! | 8.4 | 5.3 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 3.1
4 | Run & Cement 16" Casing - Perform LOT | 4.5 | 2.9 | #REF! | 12.9 | 8.2 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 4.7
5 | Drill 14-3/4" x 16-1/2" Hole Section | 3.8 | 2.4 | #REF! | 16.7 | 10.6 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 6.1
6 | Run & Cement 13-5/8" Liner - Drill Out - Perform LOT | 5.5 | 3.4 | #REF! | 22.2 | 14 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 8.2
7 | Drill 12-1/2" x 14" Hole Section | 4.3 | 3.2 | #REF! | 26.5 | 17.2 | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | 9.3
8 | Contingency Run Expandable Liner 11-7/8" x 13-5/8" | 3.7 | 0 | #REF! | 30.2 | 17.2 | #REF! | #REF! | #REF! |  |  | #REF! | #REF!
9 | [13 empty] | 0
| TOTALS : | 30.2 | 17.2 | #REF!
| Totals in hours | 724.8 | 412.8 | #REF! |  |  |  | #REF! |  | 0
| Total Days | 86.875
| Projected Bonus Time (w/ Scope Changes) | #REF! |  |  | 2010-01-31 |  |  | Scope Changes | item | Time, days
[5 empty] | 2010-04-27 21:00 |  |  |  | 3D VSP | #REF! | includes BOP Test time that could have been eliminated
| Projected Bonus | #REF!
| Total to budget for DIMS | #REF!
[9 empty] | Total | #REF!

## Data sheet just for the chart (hidden)
Graph data - automatic
|  | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9
| Run & Cement 18" Casing - Drill Out - Perform LOT |  |  | Hurricane |  |  | Drill 16-1/2" x 20" Hole Section |  |  | Run & Cement 16" Casing - Perform LOT |  |  | Drill 14-3/4" x 16-1/2" Hole Section |  |  | Run & Cement 13-5/8" Liner - Drill Out - Perform LOT |  |  | Drill 12-1/2" x 14" Hole Section |  |  | Contingency Run Expandable Liner 11-7/8" x 13-5/8" |  |  | Drill 10-5/8" x 12-1/4" Hole Section
| Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual | Eng. Target | Target | Actual
Cum. Plan Previous Sections | 4.6 |  |  | 4.6 |  |  | 4.6 |  |  | 8.4 |  |  | 12.9 |  |  | 16.7 |  |  | 22.2 |  |  | 26.5 |  |  | 30.2
Cum. Actual Previous Sections |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF!
Plan for the section (column D) |  |  |  | 0 |  |  | 3.8 |  |  | 4.5 |  |  | 3.8 |  |  | 5.5 |  |  | 4.3 |  |  | 3.7 |  |  | 4.2
Actual for the section (column F) |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF! |  |  | #REF!
Cum. Targets Previous sections |  | 2.9 |  |  | 2.9 |  |  | 2.9 |  |  | 5.3 |  |  | 8.2 |  |  | 10.6 |  |  | 14 |  |  | 17.2 |  |  | 17.2
Target for the section (column E) |  |  |  |  | 0 |  |  | 2.4 |  |  | 2.9 |  |  | 2.4 |  |  | 3.4 |  |  | 3.2 |  |  | 0 |  |  | 3.2