## Open Recommendations
P.O. Box 577 Brookshire, Texas 77423 U.S.A. |  | ISO 9001:2008 Certified | [5 empty] | Tel: (281) 934-1500 Fax: (281) 934-1600 west@westengineer.com
Section 3: WEST Recommendation Summary and Disposition
GSF Development Driller II, Job #3940; 14 May to 10 June 2010
Prepared for BP
Revision 1
Purpose: During the assessment process, WEST makes various comments and recommendations aimed towards improving safety and increasing equipment reliability. In conformance with API and ISO standards, WEST follows up on these recommendations to ensure their satisfactory resolution. To expedite this process, WEST maintains this living document that is updated during each assessment. This allows WEST to effectively manage the recommendations so the same issues are not repeated once a satisfactory resolution is in place. Any time the status changes or comments are added, the results should be forwarded to WEST so the master file can be updated. The definitions used for each recommendation priority level are as follows:
Priority I: |  | Critical items that have a significant risk of failure, well control event and/or personnel injury, and must be corrected immediately. Customer will be notified of any Priority I issues by the surveyor’s technical supervisor in WEST’s main office.
Priority II: |  | Major items that have a significant risk of causing downtime or lowering safety and should be completed within the next six months or three wells. In many cases, these items are critical to long-term equipment reliability.
Priority III: |  | Minor items that relate primarily to regulations, rig management, quality assurance issues and good oilfield practice. As these issues are unrelated to existing equipment condition, they have a low level of risk. These should be completed as soon as time permits.
Item No | Priority |  | Class | Reference |  |  |  |  | Date
|  | Recommendation |  | Job # | Surveyor Initials | ATP | Daily Report | Comments/Status | Opened | Closed | Estimated Completion
1 | II | The lower annular cap and mandrel were lifted from the lower annular body after releasing the cap latches. The element was lifted to the deck and the upper chamber head and piston also removed and lifted to the deck for inspection. After cleaning, the piston was found to have numerous scores and scratches around the entire periphery of the outside diameter that the open chamber head and cap seals ride on. These scores and scratches were dressed out as far as possible. Transocean should consider replacing the Hydril GX lower annular piston at the earliest opportunity. | BOP-Annular | 3940 | GP |  | DR 2 | New piston fitted after failed chamber test. Jun-10 GP | 2010-05-10 | 2010-06-10
2 | II | Consider obtaining a TAM packer or modified riser running tool for stump testing the annular cap seal of the Hydril GX upper annular BOP. The wellbore seal in the annular cap of the upper annular does not see pressure until the BOP is run and the riser is filled with mud. This hydrostatic differential pressure can be considerable in deep water and the seal is untested before the BOP is run. | BOP-Annular | 3940 | GP |  | DR 17 |  | Jun-10
3 | II | While making repairs to the upper shear ram port side MPL, a visual inspection shows the chrome plating, where the cylinder head attaches to the body, is starting to deteriorate. The bad spots were polished before reassembly. It is recommended for this to be monitored for further deterioration. | BOP-Rams | 3876 | MN |  | DR 9 | Replaced with refurbished bonnet. May-10 MN | Mar-10 | May-10
4 | II | During the last well, the rig experienced problems with the lower pipe rams. The rams did not operate properly when going from the close to open position. The times were slow and the gallon counts were high. The BOP had been on bottom for approximately nine months and records indicate that the lower pipe rams had 129 cycles on them. Hydril recommends that the MPL thrust bearings be replaced once a year or after 120 cycles. It is recommended that the manufacturer’s recommended maintenance be performed on the ram MPL thrust bearings when they reach 120 cycles. | BOP-Rams | 3876 | MN |  | DR 12 | Refurbished bonnets fitted. Mar-10 MN | Mar-10 | May-10
5 | II | Suggest TOI consider replacing the pressure biased shuttle valves on the open side of the casing shear rams and lower blind shear rams with pilot operated SPM types valves. | Controls | 3940 | GP |  | DR 18 |  | Jun-10
6 | II | The blue MUX reel sheave is supported by slings. It is recommended that a beam trolley should be installed like the yellow MUX cable sheave. Reference WEST ITP #128, MUX Controls Between Well Maintenance Checklist. | Controls | 3876 | MN | ATP 321 |  | The blue MUX reel sheave is supported by slings. A beam trolley should be installed like the yellow MUX cable sheave.Mar-10 MN No change. Jun-10 GP | Mar-10
7 | III | Suggest TOI consult Hydril Controls and instigate a feasibility study as to the practicality of the inclusion of ROV observable analogue pressure gauges in the MUX pods to monitor the critical operating pressures within the pod. This should include, but not limited to, annular and manifold read back pressures, pod supply pressure, and subsea accumulator pressure. | Controls | 3940 | GP |  | DR 18 |  | Jun-10
8 | III | It is recommended that the rig perform an accumulator volume test per API RP 53. After opening and closing all rams and one annular BOP, the remaining accumulator pressure shall be 1,700 psi for 5,000 psi systems. The accumulator system must meet this requirement without any pump assistance. Reference MMS CFR Title 30, Chapter II, Section 250.442, Paragraph (c), API RP 53, 3rd Edition, Section 13.3.2. | Controls | 3876 | MN | ATP 512 | DR 14 |  | Mar-10
9 | II | Transocean should consider the inclusion of an automatic changeover system for the slip joint packers to automatically energize the lower packer if the top slip joint packer should fail. This is an environmental impact issue with the use of oil based mud. | Mud System | 3940 | GP |  | DR 6 |  | Jun-10
10 | II | Verify that where rigid lines are used, target flanges are installed on short radius pipe bends (R/d<10), 90 degree bends, elbows and tees in the direction of flow. | Mud System | 3940 | GP | ATP 181 |  | 90° bends on both kill and choke lines above LMRP stabs and isolation valves are not targeted. Jun-10 GP | Jun-10
11 | II | The remote choke accumulator volumetric capacity, if equipped, shall be able to operate the choke from fully-open to fully-closed and return to fully-open. | Mud System | 3940 | GP | ATP 405 |  | No/low precharge in choke operating accumulators, no volume to operate choke. Jun-10 GP | May-10
12 | III | It was noted that the diverter flowline seals were not protected from the damaging influence of sunlight and the elements or mechanical damage. It is recommended that the diverter flowline seals are protected from the elements and mechanical damage. At a minimum, grease should be applied to the flowline seals and a protective cover placed over the flowline seals. | Mud System | 3940 | DM |  | DR 5 | Protection fitted OK. Jun-10 GP | 2010-05-10 | 2010-06-10
13 | III | Suggest TOI consider developing a method of testing the moonpool drape hoses and goosenecks off the critical path. At present, it is only possible to test the hoses and goosenecks when made up to the slip joint just before landing the BOPs on the wellhead, and the test pressure is limited to the choke and kill line test pressure while running riser. | Mud System | 3940 | GP |  | DR 18 |  | Jun-10
14 | II | Verify the telescopic joint packers are pressure tested in accordance with the manufacturer's recommendations. | Operational Management | 3940 | GP | ATP 348 |  | TJ Packer not tested. Jun-10 GP | Jun-10
15 | II | It is recommended to wellbore pressure test each component as applicable after the secondary system has been activated. This is especially critical concerning the shear rams and will prove the secondary system is capable of securing the well. Reference MMS Safety Alert No. 186. | Operational Management | 3876 | MN | ATP 205, 522 |  | ROV panels were function tested but not for wellbore testing. Mar-10 MN All ROV panels functioned and chart recorded using ROV pump. Visual on rams, no test. MMS witness. Jun-10 GP | Mar-10 | Jun-10
16 | III | Suggest TOI consider obtaining a back-up nitrogen intensifier for charging the subsea accumulators. | Operational Management | 3940 | GP |  | DR 19 |  | Jun-10
17 | III | To prevent damage to the choke and kill connectors, ensure LMRP to receiver plate guidance includes close tolerance alignment pins and collars which are engaged prior to the choke and kill connectors coming into contact. | Operational Management | 3940 | GP | ATP 152, 165 |  | No close tolerance pins used. Jun-10 | Jun-10
18 | III | Ensure that safety relief valves have been tested according to an established procedure. The procedure shall include test conditions and equipment, safety and recording experience data. Each relief valve shall be tagged. | Operational Management | 3940 | GP | ATP 222 |  | Not all tagged. Jun-10 GP | Jun-10
19 | III | Transocean should continue to work with Hydril to expidite the update of the control system drawings. Management of change and up-to-date schematics reflecting modifications to pods etc. were not available for review at the time of survey. | Operational Management | 3940 | GP | ATP 49 |  |  | May-10
20 | III | It is recommended that a low pressure chart recorder and gauge be used when performing hydraulic operator tests and signature tests. Test pressure measurements shall be made at no less than 25% or more than 75% of the full pressure span of the gauge. Reference API RP 53, 3rd Edition, Section 18.3.6; API Spec 16A, 3rd Edition, Section 8.2.2 and API Spec 16C, 1st Edition, Section 6.1.2.2. | Operational Management | 3876 | MN | ATP 45 | DR 7 | Chart recorder for operating chamber tests and pressure tests is not adequate for low pressure testing. Mar-10 MN Now have low pressure chart recorder in use. Jun-10 GP | Mar-10 | Jun-10
21 | III | The certs for the moonpool booster and moon pool conduit blue hose are missing and should be located. Reference API Spec 16C, 1st Edition, Sections 1.2.1 and 9.14. | Operational Management | 3876 | MN | ATP 184 |  | Missing certs for the moonpool booster and moonpool conduit blue. Mar-10 MN | Mar-10
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965

## Closed Recommendations
Item No | Priority |  | Class | Reference |  |  |  |  | Date
|  | Recommendation |  | Job # | Surveyor Initials | ATP | Daily Report | Comments/Status | Opened | Closed | Estimated Completion
1 | II | It is recommended that the rig change out the piston in the upper annular the next time the BOP is pulled for between well maintenance. | BOP-Annular | 3876 | MN |  | DR 2 | Piston was changed out during this between well maintenance. MN Mar-10 | Mar-10 | Mar-10
2 | I | It is recommended, by the manufacturer, to apply a light coat of Teflon filled grease (Magnalub-G or Aqualube) to the threads of the overhauling nut and screw during reassembly of the MPLs. | BOP-Rams | 3876 | MN |  | DR 3 | Aquashield was used during this assembly. MN Mar-10 | Mar-10 | Mar-10
3 | I | It is recommended that during reassembly of the MPLs, the outer thrust bearing should be thinly lubricated and set on the overhauling nut. Improper installation may result in improper performance of the MPL. | BOP-Rams | 3876 | MN | ATP 93 | DR 3 | This was performed during assembly. MN Mar-10 | Mar-10 | Mar-10
4 | I | It is recommended for the rig to have the cut on the port side casing shear body repaired. The cut is 50% into the bonnet gasket sealing area. The Hydril service representative and Transocean are deciding on a plan of action for repairing the damaged area. | BOP-Rams | 3876 | MN |  | DR 2 | The casing shear body was repaired. MN Mar-10 | Mar-10 | Mar-10
5 | II | It is recommended that after the wellbore testing is completed, a predictive unlocking test be performed on the connectors. The unlocking pressure should be checked against ABB Vetco allowable. | BOP-Rams | 3876 | MN | ATP 43, 116, 137 | DR 13 | This was performed before running the BOP. MN Mar-10 | Mar-10 | Mar-10
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!